## Eng Weekly report
Weekly Summary Report
Shaft | Nchwaning 2 | [6 empty] | Plan YTD | Actual YTD | Plan MTD | Actual MTD | Variance
[8 empty] | 1031803 | 926688 | 93497 | 83640 | -9857
Week - Date to | 2026-02-13 | 2026-02-20 |  |  |  |  | Product | 916813 | 881752 | 82778 | 75746 | -7032
Safety
| YTD | No wk | Remarks
MTC | 1 | 0
LTI | 0 | 0
PD | 6 | 1 | LD0411 -Roll Bar damaged on nightshift of 13 Februrary.
Incidents Reported | 1 | 1 | FL120 bumped a ventilation pipe while loading Tuesday afternoon, 17 Februrary
Labour
| Plan | Actual | Leave | Not Specified | % AT Work |  | Remarks
Fri |  |  |  | 0 | #DIV/0!
Mon |  |  |  | 0 | #DIV/0!
Tue |  |  |  | 0 | #DIV/0!
Wed |  |  |  | 0 | #DIV/0!
Thur |  |  |  | 0 | #DIV/0!
Sat |  |  |  | 0 | #DIV/0!
Sun |  |  |  | 0 | #DIV/0!
Cost
Remarks
The Section is not linked yet to my name on QlikView
Planned Weekend/Public Holiday Work
Description |  |  |  |  | Done | Not Done | Remarks
Repairs on fixed jaw liners on 2 West Crusher
Annual fire suppresion service on Graben belts
Pull Seam 1 from the Silo bottom and cleaning of 2West belt
Liners on the dead box at the Tire in
Crusher liners ar 2West plant (canopy)
Tip 2 Cap liners (2 West)
74 W and 17 S Upper leaky feeder cable installation.
RT38 Telescopic replacement
HD35 and RT32 service
FL102 transmission mounting
DT120 tappet cover oil leak
FL085 Exhaust mainfold
| Fri | Mon | Tue | Wed | Thu | Average
DT | 81% | 82% | 79% | 85% | 88% | 83% | DT121 - OEM is onsite and busy with the machine.
FL | 90% | 88% | 92% | 76% | 95% | 88.2%
HD | 97% | 91% | 95% | 85% | 91% | 91.8%
RT | 86% | 100% | 87% | 90% | 92% | 91%
SR | 78% | 83% | 94% | 91% | 83% | 85.8%
| 96% |  |  |  |  | 96%
TMM Status SOS (Friday Morning) : | [12 empty] | 5042
Plan
HD | 6 | 5 | HD65- cable damaged
RT | 6 | 6
DT | 9 | 8 | DT121 - Technician busy on site
FL | 6 | 6
SR | 6 | 6
Charge up UV`s | 3 | 3 | UV108 is going to be test as from today. UV137 is switched to Level 7 as from Tuesday during day shift.
RORO/Flat deck UV`s | 3 | 3
Weekly Primary TMM Maintenance Overview
Challenges
ECS and Strata are struggling to sort out CAS Level 9 problem with UV137. The data had been taken for further analyisis

## Compliance Report
Weekly Asset Care Compliance Report
Don’t change Formula's
| Week Ending | 2026-02-19
| Shaft / Area | NCHW II UG
| Fleet / Equipment | Planned | Actual | Schedule Compliance | Target | Unit late for service (y/n) | Unit book back on time after service(y/n) |  | Week-end Service | Reasons for Non-Compliance
| DT | 4 | 4 | 100% | 100%
| FL | 4 | 4 | 100% | 100% |  |  |  |  | Due to loader availability and was rescheduled for next week
| HD | 4 | 3 | 75% | 100%
| RT | 2 | 2 | 100% | 100% |  |  |  |  | HD0063 Planned for next week, due to labour shortage at Graben
| SR - Service Compliance | 1 | 1 | 100% | 100%
| Support Equipment | 5 | 5 | 100% | 100% |  |  |  |  | EXCLUDE UV0053 :STILL OUT FOR LEVEL 9 UPGRADE
| SR - Weekly Inspection | 8 | 8 | 100% | 100%
Service Pre-Inspection
| Fleet / Equipment | Planned | Actual | Schedule Compliance | Target | Work order number | Remarks
| DT | 1 | 1 | 100% | 95%
| FL | 1 | 1 | 100% | 95%
| HD | 3 | 3 | 100% | 95%
| RT | 3 | 3 | 100% | 95%
| SR - Service Compliance | 1 | 1 | 100% | 95%
| Support Equipment | 7 | 5 | 71.43% | 95% |  | LD0508 broken universal joint on front diff and LD0576 will be service tonight
Condition monitoring / Oil samples
| Fleet / Equipment | Engine - Plan | Engine- Received | Transmission - Plan | Transmission - Receive | Axle - plan | Axle - Receive | % Compliance | Reasons for Non-Compliance |  |  | Paperwork Correct | Paperwork Incorrect | Urgent Oil Samples | Workorder Generated
| DT | 4 | 4 | 4 | 4 |  |  | 100% | [5 empty] | 0
| FL | 4 | 4 | 4 | 4 |  |  | 100% | [5 empty] | 0
| HD | 0 | [11 empty] | 0
| RT | 0 | [11 empty] | 0
| SR | 1 | 1 |  |  |  |  | 100% | [5 empty] | 0
| Support Equipment | 5 | 5 |  |  |  |  | 100% | EXCLUDE UV0053 :STILL OUT FOR LEVEL 9 UPGRADE |  |  |  |  | 0
Remember Readings
Oil Filtration
FA0007 - HYDR DRILL W/S | Equipment nr | Oil Type | Start Reading | End Reading | Comments |  | ISO Standard
| HD0046 | AZOLLA | 20.19.16 | 17.13.9
| RT0038 | AZOLLA | 22.21.16 | 18.16.11
| HD0064 | AZOLLA | 20.18.14 | 18.15.10
| HD0065 | AZOLLA | 22.20.16 | 21.19.13
FA0001 - TMM W/S | DT0169 |  | ,11/7/0 | ,18/14/0 |  |  |  | Filtration not done on other TMM, we replaced stranmission screen folter and drained the oil, refill with new oil.
| Inspection done by: | Planned Over-Inspections | Total Number of Inspections Completed | Corrective Work | Wo Number | % Completed | Remarks for not comply
| UTILITY FOREMAN | 7 | 5 |  |  | 71.43% | LD0508 broken universal joint on front diff and LD0576 will be service tonight
| MECHANIC FOREMAN | 8 | 8 |  |  | 100%
| DRILLS FOREMAN | 6 | 6 |  |  | 100%
| Engineer | 1 | 1 |  |  | 100%
| Electrical Foreman | 4 | 4 |  |  | 100%
| Plant Foreman | 5 | 5 |  |  | 100%
| GES Plant | 1 | 1 |  |  | 100%
| GES TMM | 1 | 1 |  |  | 100%
| Equipment ID | Date of Inspection | Inspection Performed by | Findings and Defects Completed |  |  | Additional Follow-up Work |  |  | WO No. | Status
| Graben SOH jaw crusher inspection | 16/02/2026 | Lebogang | All in order |  |  | None |  |  | 1922542
| Nch2 U/G Silo system inspection | 16/02/2026 | Lebogang | All in order |  |  | None |  |  | 1921834
| Foreman Monthly workshop inspection | 17/02/2026 | Lebogang | All in order |  |  | None |  |  | 1922724
| Monthly Fire Extinguisher inspection | 17/02/2026 | Lebogang | All in order |  |  | Annual service to be done next month. Replace all Fire Extinguishers. |  |  | 1922727
| Monthly PTO's | 18/02/2026 | Lebogang |  | All in order |  |  | None |  | 1922726
| RT0043 | 14/02/2026 | WILL | All in order |  |  | None
| HD0046 | 16/02/2026 | WILL | All in order |  |  | None
| RT0038 | 17/02/2026 | WILL | Telescopic Set worn out |  |  | Replace Telescopic Set
| HD0064 | 18/02/2026 | WILL | All in order |  |  | Monitor electrical trips
| HD0065 | 19/02/2026 | WILL | All in order |  |  | None
| HD0046 | 16/02/2026 | Shaied | None |  |  | IO
| HD0064 | 18/02/2026 | Shaied | None |  |  | IO |  |  | 1922416
| HD0065 | 19/02/2026 | Shaied | None |  |  | IO |  |  | 1923891
| SOH -Tripper Car Insp | 19/02/2026 | Shaied | None |  |  | IO |  |  | 1923055
| LD0621 | 11/02/2026 | FJ Scheeper | None |  |  | IO |  |  | 1921745
| UV0059 | 13/02/2026 | Petrus -91030700 | None |  |  | IO |  |  | 1907305
| SR0029 | 16/02/2026 | Innocent Dlamini - 10065782 | None |  |  | IO |  |  | 1874264
| LD0519 | 17/02/2026 | Didi Lekwa-10064475 | fuel tank bracket broken | [5 empty] | 1936512
| UV0098 | 18/02/2026 | Obakeng Kokonyane | rear prophshaft | [5 empty] | 1937316
| FL0106 | 10/02/2026 | Gae | damages grease hoses, oil leaks | [5 empty] | 1896410
| FL0114 | 13/02/2026 | Gae |  |  |  | front loghts harnes |  |  | 1925310
| FL0120 | 14/02/2026 | Gae | [6 empty] | 1912685
| FL0100 | 19/02/2026 | Gae | kenru defect hoses,grease system | [5 empty] | 1917699
| DT0120 | 14/02/2026 | Gae | loghts, damaged transmission bonnet |  |  | rear lights and bucket switcth harness |  |  | 1925304
| DT0169 | 16/02/2026 | Gae | 500hours service | [5 empty] | 1921740
| DT0181 | 17/02/2026 | Gae | 250 hours service |  |  | wiper motor,cracked side window |  |  | 1930877
| DT0176 | 18/02/2026 | Gae | 250 hours service | [5 empty] | 1936669
| 28N Section | 17/02/2026 | Mteki | VFL and section condition inspections |  |  | Power was tripping

## Water Consumption
Water Consumption Management
Dates: 13 Feb. -20 Feb. | Shaft |  | Fire Dams
Water Type | Down | Out | In | Out
Process | 0 | 9221
Portable | 298
Fire |  |  |  |  | Fire figures are not available yet

## Quality Report
Weekly Asset Care Compliance Report Nchwaning II UG
| Week Ending | 2026-02-19 | [6 empty] | NB: PLEASE DO NOT EDIT ON YELLOW COLUMN
| Shaft / Area | Nch II U/G
Weekly Quality Service Report
|  |  | Mining |  |  |  | 64.58% | Engineering | [5 empty] | 80.83%
| Schedule Date | TMM Unit Number | Actual Time Available In Workshop - < 7:00 AM | 07:00 AM - 50% 08:00 AM - 25% 09:00 AM - 0% | Machine Clean for Maintenance | No - 0% Yes - 50% |  | Pre inspection & Operator Engagement - 3 Days Before Service Done | No - 0% Yes - 25% | Actual Service Duration - Plan 6 Hours | 6Hrs - 50% 5Hrs - 40% 4Hrs - 30% 3Hrs - 20% 2Hrs - 10% 1Hrs - 0% | Machine Tested and Over Inspected by Supervisor | No - 0% Yes - 25% |  | Time of first breakdown | Completed Service Workorder number | Actual Hrs on service date
1 | 2026-02-13 | DT0120 | 8:00 | 25% | Yes | 50% | 75% | Yes | 25% | 6hrs | 50% | Yes | 25% | 100% |  | 1925304
2 | 2026-02-13 | FL0120 | 8:00 | 25% | Yes | 50% | 75% | Yes | 25% | 5hrs | 40% | Yes | 25% | 90%
3 | 2026-02-13 | HD0063 |  |  |  |  | 0% | [6 empty] | 0%
4 | 2026-02-13 | RT0043 | 8:00 | 25% | Yes | 50% | 75% | Yes | 25% | 6hrs | 50% | Yes | 25% | 100% | 19.1 | 1923302 | 3782
5 | 2026-02-13 | UV0059 | 8:00 | 25% | Yes | 50% | 75% | Yes | 25% | 6 | 50% | Yes | 25% | 100%
6 | 2026-02-13 | LD0621 | 7:00 | 50% | Yes | 50% | 100% | Yes | 25% | 6 | 50% | Yes | 25% | 100%
7 | 2026-02-16 | DT0169 | 9:00 | 0% | Yes | 50% | 50% | Yes | 25% | 5hrs | 40% | Yes | 25% | 90%
8 | 2026-02-16 | FL0106 | 9:00 | 25% | Yes | 50% | 75% | Yes | 25% | 5hrs | 50% | Yes | 25% | 100%
9 | 2026-02-16 | HD0046 | 8:00 | 25% | Yes | 50% | 75% | Yes | 25% | 6hrs | 50% | Yes | 25% | 100% | 2.21 | 1923887 | 3723
10 | 2026-02-16 | SR0029 | 7:00 | 50% | Yes | 50% | 100% | Yes | 25% | 6 | 50% | Yes | 25% | 100%
11 | 2026-02-16 | LD0508 |  |  |  |  | 0% | [6 empty] | 0%
12 | 2026-02-17 | DT0181 | 8:00 | 25% | Yes | 50% | 75% | Yes | 25% | 5hrs | 40% | Yes | 25% | 90%
13 | 2026-02-17 | FL0114 | 9:00 | 25% | Yes | 50% | 75% | Yes | 25% | 5hrs | 40% | Yes | 25% | 90%
14 | 2026-02-17 | RT0038 | 8:00 | 25% | Yes | 50% | 75% | Yes | 25% | 6hrs | 50% | Yes | 25% | 100% | 4 | 1923945 | 2399
15 | 2026-02-18 | DT0176 | 8:00 | 25% | Yes | 50% | 75% | Yes | 25% | 5hrs | 50% | Yes | 25% | 100%
16 | 2026-02-18 | HD0064 | 8:00 | 25% | Yes | 50% | 75% | Yes | 25% | 6hrs | 50% | Yes | 25% | 100% | 0.4 | 1922408 | 1474
17 | 2026-02-18 | LD0576 |  |  |  |  | 0% | [6 empty] | 0%
18 | 2026-02-19 | FL0100 | 9:00 | 25% | No | 50% | 75% | Yes | 25% | 6hrs | 50% | Yes | 25% | 100%
19 | 2026-02-19 | HD0065 | 8:00 | 25% | Yes | 50% | 75% | Yes | 25% | 6hrs | 50% | Yes | 25% | 100% | 1 | 1923888 | 1655
20 | 2026-02-19 | UV0098 | 7:00 | 50% | Yes | 50% | 100% | Yes | 25% | 6 | 50% | Yes | 25% | 100%
21 | [6 empty] | 0% | [6 empty] | 0%
22 | [6 empty] | 0% | [6 empty] | 0%
23 | [6 empty] | 0% | [6 empty] | 0%
24 | [6 empty] | 0% | [6 empty] | 0%
25 | [6 empty] | 0% | [6 empty] | 0%
26 | [6 empty] | 0% | [6 empty] | 0%
27 | [6 empty] | 0% | [6 empty] | 0%
28 | [6 empty] | 0% | [6 empty] | 0%
29 | [6 empty] | 0% | [6 empty] | 0%
30 | [6 empty] | 0% | [6 empty] | 0%
31 | [6 empty] | 0% | [6 empty] | 0%
32 | [6 empty] | 0% | [6 empty] | 0%
33 | [6 empty] | 0% | [6 empty] | 0%
Note on X8: Rahab Makolomakwa: Use this tab as requested by the engineering manager. HD & RT only, MTBF after service.
Note on N9: Botshelo Gae: operators are not available during the pre inspection

## Fermel Weekly
|  | N 2 |  | Fer
No | Area / Owner | TMM Type | TMM No. | Breakdown | Comment | OEM Assistance Required |  | Utility Machine | Total | Breakdown | Availabile
| RORO UV'S FERMEL | [6 empty] | Maverick Dble Cab STD Load Bin | 11 | 1 | 90.91%
2 | BRP/Logistics | Liberator Roll On Roll Off | UV0054 |  | Available |  |  | Maverick Man Lift | 4 | 1 | 75%
3 | BRP/Logistics | Liberator Roll On Roll Off | UV0059 |  | Available |  |  | Liberator Roll On Roll Off | 6 | 0 | 100%
4 | Roadways | Liberator Roll On Roll Off | UV0061 |  | Available |  |  | Placer dumper | 1 | 0 | 100%
5 | BRP/Logistics | Liberator Roll On Roll Off | UV0118 |  | Available |  |  | Maverick king Cab c/w Crane | 3 | 0 | 100%
6 | BRP/Logistics | Fermel Placer Dumper | UV0119 |  | Available |  |  | Maverick Single cab Jam Pot | 1 | 0 | 100%
7 | BRP/Logistics | Liberator Roll On Roll Off | UV0120 |  | Available |  |  | Maverick 12 Man Trooper | 3 | 0 | 100%
8 | BRP/Logistics | Liberator Roll On Roll Off | UV0133 |  | Available |  |  | Scaler | 8 | 0 | 100%
| MAVERICK UV'S | [6 empty] | Toyota landcuiser ambulance | 1 | 0 | 100%
10 | Williams /drill mec | Maverick King Cab NO Crane | UV0069 |  | Available |  |  | Maverick king Cab with no Crane | 2 | 0 | 100%
11 | Kal Tire | Maverick King Cab NO Crane | UV0072 |  | Avaiable |  |  | Toyota landcruiser | 36 | 2 | 94.44%
12 | Williams | Maverick king Cab c/w Crane | UV0087 |  | Available |  |  |  | 76 | 4 | 94.74%
13 | Fitters | Maverick king Cab c/w Crane | UV0090 |  | Available
14 | Gae | Maverick king Cab c/w Crane | UV0092 |  | Available
15 | Sanitation | Maverick Single cab Jam Pot | UV0102 |  | Available
MAVERICK LDO'S
17 |  |  | LD0378
18 | Roadways | Maverick Dble Cab STD Load Bin | LD0407 |  | Available
19 | Williams /drill mec | Maverick Dble Cab STD Load Bin | LD0408 |  | Available
20 | Mining/28 section | Maverick Dble Cab STD Load Bin | LD0411 |  | Available
21 | Technicians | Maverick Dble Cab STD Load Bin | LD0414 | Strata system repaired. Flasher faulty. | Available |  | Labour for the week including Nightshift
22 | Themba fire fighters | Maverick Dble Cab STD Load Bin | LD0415 | Coolant topped up and machine was tested. | Available |  | Foreman | 1 of 0 |  | x1 relieving
23 | Boilermakers | Maverick Dble Cab STD Load Bin | LD0419 |  | Available |  | Chargehand | 1 of 0 |  | x1 relieving
24 | Technicians | Maverick Dble Cab STD Load Bin | LD0426 | Engine replaced, outstanding parts were ordered WO(1930761) auto electrician started with checking and repairing wiring and mechanic started with replacing of mechanical parts. | Not Available |  | Mechanics | 10 of 5 | 4 | x2sick,annual leave,x1relieving
25 | Explosive | Maverick Dble Cab STD Load Bin | LD0450 |  | Available |  | Auto Electrician | 3 of 2 | 2 | X1 Night shift
26 | Capital graben | Maverick Dble Cab STD Load Bin | LD0508 |  | Available |  | Semi skilled | 3 of 2 | 1 | x1 Annual leave
27 | Gae | Maverick Dble Cab STD Load Bin | LD0509 |  | Available |  | Leaners | 1 of 1
28 | Capital graben | Maverick Dble Cab STD Load Bin | LD0519 |  | Available
29
30
32
33
34
35
36
37
| MAVERICK LDO'S TROPPER | [5 empty] | DELAY:
39 | Fitters | Maverick 12 Man Trooper | LD0477 |  | Available
40 | Mining/28 section | Maverick 12 Man Trooper | LD0523 |  | Available
41 | Construction | Maverick 12 Man Trooper | LD0532 |  | Available
42 | MAVERICK UV'S MANLIFTS | [5 empty] | PRIORITY FOR THE NEXT SHIFT
43 | Geologist | Maverick Man Lift | UV0077 | The machine must be moved to Fermel Head Office for refurbishment of the bucket harness and front outriggers. | Not Available
44 | Survey | Maverick Man Lift | UV0098 |  | Available
45 | Survey | Maverick Man Lift | UV0099 |  | Available
46 | Geologist | Maverick Man Lift | UV0123 |  | Available |  | SERVICE UPDATES
TOYOTA CRUISER LDO'S
47 | Ambulance | Toyota Cruiser 4x4 emergency vehicle | LD0 341 |  | Available
48 | Capital graben | Toyota Cruiser 4x4/Trimming-Connie | LD0 553 |  | Available
49 | Lebolo/2west2body | Toyota Cruiser 4x4/mining -Lebelo | LD0 554 |  | Available
50 | Connie Trimming | Toyota Cruiser 4x4/Trimming-Connie | LD0 557 |  | Available
51 | Fitters w/shop | Toyota Cruiser 4x4/fitter plant-Lebogang | LD0 575 |  | Available
52 | Electrical w/shop | Toyota Cruiser 4x4 /electrician-Hansie | LD0 576 |  | Available
53 | Connie Mining | Toyota Cruiser 4x4/mining-Connie | LD0 577 |  | Available
54 | Peace | Toyota Cruiser 4x4/mining -portgter | LD0 578 |  | Available
55 | Christo | Toyota Cruiser 4x4/mining-christo | LD0 579 |  | Available
56 | Training Center | Toyota Cruiser 4x4/training center | LD0 580 |  | Available
57 | Potgieter | Toyota Cruiser 4x4/Mining 28 section | LD0 581 |  | Available
5
55
56
AARD UV'S
58 | Duba Utility | aard-uv60-diesel tank | UV0053 | Machine send for L9 Compliance. | Not Available
59 | Hansie Louw | aard-uv60 | UV0084 |  | Available
| Roadways | aard-uv80-water tank truck | UV0121 |  | Available
61 | Capital-Graben | aard-uv80 | UV0130 |  | Available
62 | Construction | aard-uv60 | UV0139 |  | Available
63 | Construction | aard-uv60 | UV0140 |  | Available
67
68
| SCALER'S |  |  |  | Available
72 | Scaler | Scaler | SR0029 |  | Available
73 | Scaler | Scaler | SR0033 |  | Available
74 | Scaler | scaler graben Capital Tel 5013 | SR0036 |  | Available
75 | Scaler | scaler 17upper 74 Portigter | SR0042 |  | Available
76 | Scaler | scaler 17upper 74 Portigter | SR0045 |  | Available
77 | Scaler | scaler graben Capital Tel 5013 | SR0046 |  | Available
| Scaler | Scaler Mining | SR0053 |  | Available
78 | Scaler | Scaler Mining | SR0054 | Front hammer cylinder leaking oil PR Created 25000584/A9 WO (01932846) for OEM to check aircon system and remove and replace cylinder. | Not Available
| TOYOTA CRUISER WITH HIAB'S |  |  |  | 3
78 | Life Tmm | Toyota Cruiser 4x4 | LD0 589* |  | Available
79 | Duba Utility | Toyota Cruiser 4x4 | LD0 590* |  | Available
80 | Didi-Boilermaker | Toyota Cruiser 4x | LD0 592* |  | Available
81 | Izak Bothman KalTire | Toyota Cruiser 4x4/Kal Tire | LD0 593* |  | Available
82 | Fitters Lebogang | Toyota Cruiser 4x4/ | LD0 594 |  | Available
83 | Duba Utility | Toyota Cruiser 4x4/ | LD0 621 |  | Available
84 | Life Tmm | Toyota Cruiser 4x4/ | LD0 633 |  | Available
TOYOTA CRUISER TROPPER'S
84 | Karl Roadways | Toyota Cruiser 4x4/ | LD0 596 |  | Available
85 | Geologist&Survey | Toyota Cruiser 4x4/ | LD0 605 |  | Available
86 | Mining-Peace | Toyota Cruiser 4x4/ | LD0 629 |  | Available
| Mining | Toyota Cruiser 4x4/ | LD0 649 |  | Available
| Duba Utility | Toyota Cruiser 4x4/ | LD0 650 |  | Available
TOYOTA CRUISER WITHOUT HIAB'S
87 | William Tel:5429 | Toyota Cruiser 4x4/ lube | LD0 591 |  | Available
88 | Duba Utility | Toyota Cruiser 4x4- single cap | LD0 621* |  | Available
89 | Electrician tel:5416 | Toyota Cruiser 4x4/ | LD0 623 |  | Available
90 | Electrician tel:5416 | Toyota Cruiser 4x4/ | LD0630* |  | Available
91 | William Tel:5429 | Toyota Cruiser 4x4/ | LD0631 |  | Available
92 | Boilers | Toyota Cruiser 4x4 | LD0634* |  | Available
93 | Izak Botham | Toyota Cruiser 4x4/ drill rod carrier | LD0636* |  | Available
| Manyafunyafu | CRUISER SINGLE CAP Hiab | LD0642 |  | Available
| William Tel:5429 | CRUISER SINGLE CAP Hiab | LD0647 | Nerospec system defective. Technician from nerospec said breakdown is on AUSCO Brakes side. | Not Available
| Life Tmm | CRUISER SINGLE CAP Hiab | LD0648 |  | Available
| Strata team | CRUISER SINGLE CAP Hiab | LD0658 |  | Available
| Project | CRUISER 8 Seater | LD0675 |  | Available

## Blocked Chute
0 | Details | FEEDER BELT CHUTE |  |  | TIPS 1&2 | [5 empty] | Area xyz
| Supervisor/artisan who assisted with unblocking | M.Diergaardt | TK Mosiane | J Benson | M.Diergaardt | TK Mosiane | J Benson | M.Diergaardt | TK Mosiane | J Benson
02/02/2026 | Reason for blockage | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages
| Time of blockage | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Supervisor/artisan who assisted with unblocking | Xaba | GKP SETSHEDI | J Benson | Xaba | GKP SETSHEDI | J Benson | Xaba | GKP SETSHEDI | J Benson
03/02/2026 | Reason for blockage | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages
| Time of blockage | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Supervisor/artisan who assisted with unblocking | Xaba | GKP SETSHEDI | J Benson | Xaba | GKP SETSHEDI | J Benson | Xaba | GKP SETSHEDI | J Benson
04/02/2026 | Reason for blockage | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages
| Time of blockage | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Supervisor/artisan who assisted with unblocking | Xaba |  |  | Xaba |  |  | Xaba
05/02/2026 | Reason for blockage | No Blockages |  |  | No Blockages |  |  | No Blockages
| Time of blockage | N/A |  |  | N/A |  |  | N/A
| Supervisor/artisan who assisted with unblocking | Xaba | GKP SETSHEDI |  | Xaba | GKP SETSHEDI |  | Xaba | GKP SETSHEDI
06/02/2026 | Reason for blockage | No Blockages | No Blockages |  | No Blockages | No Blockages |  | No Blockages | No Blockages
| Time of blockage | N/A | N/A |  | N/A | N/A |  | N/A | N/A
| Supervisor/artisan who assisted with unblocking | L OOR | GKP SETSHEDI | Xaba | L OOR | GKP SETSHEDI | Xaba | L OOR | GKP SETSHEDI | Xaba
09/02/2026 | Reason for blockage | wedged and pile up |  |  | No Blockages |  | No Blockages | No Blockages |  | No Blockages
|  | of flat big rocks | No Blockages | No Blockages | N/A | No Blockages |  | N/A | No Blockages
| Time of blockage | 10h30-10h54&11h45-12h00 | N/A | N/A |  | N/A | N/A |  | N/A | N/A
| Supervisor/artisan who assisted with unblocking | J Benson | TK Mosiane | Xaba | J Benson | TK Mosiane | Xaba | J Benson | TK Mosiane | Xaba
10/02/2026 | Reason for blockage | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages
| Time of blockage | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Supervisor/artisan who assisted with unblocking | J Benson | TK Mosiane | Xaba | J Benson | TK Mosiane | Xaba | J Benson | TK Mosiane | Xaba
11/02/2026 | Reason for blockage | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages
| Time of blockage | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Supervisor/artisan who assisted with unblocking | J Benson | TK Mosiane | Xaba | J Benson | TK Mosiane | Xaba | J Benson | TK Mosiane | Xaba
12/02/2026 | Reason for blockage | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages
| Time of blockage | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
13/02/2026 | Supervisor/artisan who assisted with unblocking | J Benson | TK Mosiane | Xaba | J Benson | TK Mosiane | Xaba | J Benson | TK Mosiane | Xaba
| Reason for blockage | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages
| Time of blockage | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
15/02/2026 | Supervisor/artisan who assisted with unblocking | J Benson |  |  | J Benson |  |  | J Benson
| Reason for blockage | No Blockages |  |  | No Blockages |  |  | No Blockages
| Time of blockage | N/A |  |  | N/A |  |  | N/A
16/02/2026 | Supervisor/artisan who assisted with unblocking | M.Diergaardt | TK Mosiane | J Benson | M.Diergaardt | TK Mosiane | J Benson | M.Diergaardt | TK Mosiane | J Benson
| Reason for blockage | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages
| Time of blockage | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
17/02/2026 | Supervisor/artisan who assisted with unblocking | Xaba | TK Mosiane | J Benson | Xaba | TK Mosiane | J Benson | Xaba | TK Mosiane | J Benson
| Reason for blockage | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages
| Time of blockage | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
18/02/2026 | Supervisor/artisan who assisted with unblocking | Xaba | TK Mosiane | J Benson | Xaba | TK Mosiane | J Benson | Xaba | TK Mosiane | J Benson
| Reason for blockage | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages
| Time of blockage | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
19/02/2026 | Supervisor/artisan who assisted with unblocking | Xaba | TK Mosiane |  | Xaba | TK Mosiane |  | Xaba | TK Mosiane
| Reason for blockage | No Blockages | No Blockages |  | No Blockages | No Blockages |  | No Blockages | No Blockages
| Time of blockage | N/A | N/A |  | N/A | N/A |  | N/A | N/A
20/02/2026 | Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
21/02/2026 | Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
22/02/2026 | Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
23/02/2026 | Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
24/02/2026 | Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
25/02/2026 | Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage