## Service Detail (hidden)
Asset Care Service Compliance
|  | Week: | 07-13 Mar 2022
|  | 2022-07-03 | 2022-08-03 | 2022-09-03 | 2022-10-03 | 2022-11-03 | 2022-12-03 | 13/3/2022
| Equipment type | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
| DT | DT0131(1261608) |  | DT0143(1264394)
| FL |  | GD0011(1255285) |  | FL0061(1217537)
| HD | HD0049 | HD0056 | HD0055 | HD0054 | HD0052
| RT | RT0039 | RT0037 | RT0035 | RT0034 | RT0033
SR
| Support Vehicles-UVs |  | UV0071(1264494) | UV0082(1264498) | UV0101(1264509) | UV0088(1264510)
UV0063(1200324)
Support Vehicles-LDVs
Completed Services
|  | Unit Number | Feedback | Service Date
|  | DT0131 | Serviced
|  | DT0143 | Serviced
|  | GD0011 | Serviced
|  | FL0061 | Not serviced,On breakdown
|  | UV0063 | Serviced
|  | UV0071 | Not serviced, Artisans attended Ausco brakes course
|  | UV0082 | Not serviced,On breakdown
|  | UV0101 | Serviced
|  | UV0088 | Serviced
| Machine nr | Reason Not Serviced | Machine nr | Reason Not Serviced
| HD0049 | Serviced | RT0039 | Serviced
| HD0056 | Serviced | RT0037 | Serviced
| HD0055 | Serviced | RT0035 | Serviced
| HD0052 | Not serviced | RT0034 | Serviced
| HD0054 | Not serviced | RT0033 | Serviced
|  | Week: | 21-24 Mar 2022
|  | 21/3/2022 | 22/3/2022 | 23/3/2022 | 24/3/2022 | 25/3/2022 | 26/3/2022 | 27/3/2022
| Equipment type | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
| DT | Holiday |  |  |  | Pay Friday Off
FL
| HD |  | HD0055 | HD0052 | HD0051
| RT |  | RT0037 | RT0035 | RT0034
SR
| Support Vehicles-UVs |  | UV0081
Support Vehicles-LDVs
Completed Services
|  |  | Unit Number | Feedback | Service Date
|  |  | UV0081 | Serviced | 23/03/2022
Date | Day | Machine nr | Reason Not Serviced | Arrival time @ w/shop | Cleaned/Not cleaned | Machine nr | Reason Not Serviced | Arrival time @ w/shop | Cleaned/Not cleaned
2022-03-22 | Tuesday | HD0055 | Serviced | Start of shift | Not cleaned | RT0037 | Serviced | Start of shift | Not cleaned
2022-03-23 | Wednesday | HD0052 | Serviced | 8:30 | Not cleaned | RT0035 | Serviced | 9:30 | Not cleaned
2022-03-24 | Thursday | HD0051 | Not serviced,breakdowns in section HD0055 Screen |  |  | RT0034 | Not serviced standing with chassis
|  |  | Week: | 28 Mar-1 Apr 2022
|  | 28/3/2022 | 29/3/2022 | 30/3/2022 | 31/3/2022 | 2022-01-04 | 2022-02-04 | 2022-03-04
| Equipment type | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
| DT | DT0145(1274114-3000 Hrs) |  | DT0108(1274199-250 Hrs)
| FL |  |  |  | FL0080(1274111-250 Hrs)
| HD | HD0050 | HD0049 | HD0056 | HD0055 | HD0054
| RT | RT0033 | RT0025 | RT0048 | RT0047 | RT0035
| SR |  | SR0026(1245825-3Mnthly serv)
| Support Vehicles-UVs | UV0086(1274186-250 Hrs) | UV0079(1268129-250 Hrs) | UV0091(1274112-250 Hrs) | UV0094(1274113-250 Hrs) | UV0046(1274106-250 Hrs)
| Support Vehicles-LDVs |  |  |  |  | LD0436(1255297-500 Hrs)
Completed Services
|  | Unit Number | Feedback | Service Date
|  | DT0145 | Serviced | 28/03/2022
|  | DT0108 | Serviced | 2022-01-04
|  | UV0086 | Serviced | 28/03/2022
|  | UV0079 | Serviced | 29/03/2022
|  | UV0091 | Serviced | 30/03/2022
|  | FL0080 | Serviced | 31/03/2022
|  | UV0094 | Serviced | 2022-02-04
|  | LD0436 | Serviced | 2022-01-04
|  | SR0026 | Serviced | 2022-03-04
Date | Day | Machine nr | Reason Not Serviced | Arrival time @ w/shop | Cleaned/Not cleaned | Machine nr | Reason Not Serviced | Arrival time @ w/shop | Cleaned/Not cleaned
2022-03-28 | Monday | HD0050 | Serviced | Start of shift | Not cleaned | RT0033 | Serviced | 10:00 | Not cleaned
2022-03-29 | Tuesday | HD0049 | Serviced | 9:00 | Not cleaned | RT0025 | Serviced | 8:45 | Not cleaned
2022-03-30 | Wednesday | HD0056 | Serviced | Start of shift | Not cleaned | RT0048 | Not Serviced
2022-03-31 | Thursday | HD0055 | Serviced | Start of shift | Not cleaned | RT0047 | Serviced | Start of shift | Not cleaned
2022-04-01 | Friday | HD0054 | Serviced | 8:30 | Not cleaned | RT0035 | Not serviced,Boom Bearing Housing
Weekly Asset Care Compliance Report
Week Ending | 2022-04-08
Shaft / Area | Nchw III U/G
Fleet / Equipment | Planned | Actual | Schedule Compliance | Target | Unit late for service (y/n) | Reasons for Non-Compliance
FL | 2 | 1 | 50% | 95% | N | FL0103 Half Arrows-Planned to be serviced today(11/04/2022)
DT | 2 | 2 | 100% | 95% | N
HD | 5 | 4 | 80% | 95% | N | HD0049 Not serviced because of power failure over the weekend
RT | 5 | 5 | 100% | 95% | N
SR | 1 | 1 | 100% | 95% | N
Support Equipment | 5 | 3 | 60% | 95% | N | UV0112 & LD0433 both not brought in for services by sections/End users
Over Inspections
Inspector | Planned Over-Inspections | Total Number of Inspections Completed | Corrective Work | Wo Number | % Completed
Mech Foreman | 2 | 2 |  |  | 100%
Hyd Drill Foreman | 9 | 9 |  |  | 100%
Utility Vehicle Foreman | 0 | 0
Electrical Foreman | 0 | 0
Plant Foreman | 0 | 0
GES | 2 | 2 |  |  | 100%
Engineer | 2 | 2 |  |  | 100%
Equipment ID | Date of Inspection | Inspection Performed by | Findings and Defects Completed |  |  | Additional Follow-up Work |  |  | WO No. | Status
RT0033 | 2022-04-08 | F Barnard | Compressor oil low |  |  | Topped up oil |  |  |  | Done
RT0033 | 2022-04-08 | F Barnard | Stinger bracket worn |  |  | Replaced bracket |  |  |  | Done
RT0033 | 2022-04-08 | F Barnard | Exhaust worn |  |  | Exhaust to be replaced |  |  |  | TBD
RT0037 | 2022-04-08 | F Barnard | Drifter piston damaged |  |  | Piston to be replaced |  |  |  | TBD
RT0037 | 2022-04-08 | F Barnard | Booyco wiring open ends |  |  | Wiring to be restored |  |  |  | TBD
RT0037 | 2022-04-08 | F Barnard | Fire extinguisher bracket defective |  |  | Bracket to be replaced |  |  |  | TBD
RT0037 | 2022-04-08 | F Barnard | Jaws bolts loose |  |  | Tightened loose bolts |  |  |  | Done
HD0052 | 2022-04-04 | F Barnard | RH Boom hoses worn |  |  | Hoses to be replaced |  |  |  | TBD
HD0052 | 2022-04-04 | F Barnard | LH Boom feed sensor bracket broken |  |  | Bracket replaced |  |  |  | Done
FL0082 | 2022-04-09 | P Izaaks | Engine overheating |  |  | Fixed and tested machine |  |  |  | Done
DT0119 | 2022-04-08 | P Izaaks | Transmission Rubbers worn |  |  | Replaced rubbers |  |  |  | Done
DT0097 | 2022-04-08 | P Izaaks | Engine overheating |  |  | Fixed and tested machine |  |  |  | Done
FL0103 | 2022-04-04 | M Mokubung | Half Arrow worn |  |  | Replaced half arrows |  |  |  | Done
Section | Number of Breakdown Jobcards | Problem / Cause Remedy Completed | Number of 5Y Required | Number of 5Y Completed | % Compliance (P/C/R) | % Compliance (5Y)
Mechanical Foreman | 76 | 0 |  | 0 | 0%
Drill Shop Foreman | 63 | 0 |  | 0 | 0%
Electrical Foreman | 6 | 0 |  | 0 | 0%
Fitter Foreman | 1 | 0 |  | 0 | 0%
Boilermaker Foreman | 5 | 0 |  | 0 | 0%
Utility Vehicle Foreman | 9 | 0 |  | 0 | 0%
Weekly Asset Care Compliance Report
Week Ending | 2022-04-15
Shaft / Area | Nchw III U/G
Fleet / Equipment | Planned | Actual | Schedule Compliance | Target | Unit late for service (y/n) | Reasons for Non-Compliance
FL | 1 | 1 | 100% | 95% | N
DT | 4 | 3 | 75% | 95% | N | DT0096 Not serviced, Service kit not available
HD | 4 |  | 0% | 95% | N
RT | 4 |  | 0% | 95% | N | RT0047 not serviced, Water pump breakdown
SR | 0 |  |  | 95%
Support Equipment | 3 |  | 0% | 95% | N
Over Inspections
Inspector | Planned Over-Inspections | Total Number of Inspections Completed | Corrective Work | Wo Number | % Completed
Mech Foreman | 6 |  |  |  | 0%
Hyd Drill Foreman | 8 |  |  |  | 0%
Utility Vehicle Foreman | 2 |  |  |  | 0%
Electrical Foreman | 8 |  |  |  | 0%
Plant Foreman
GES
Engineer
Equipment ID | Date of Inspection | Inspection Performed by | Findings and Defects Completed |  |  | Additional Follow-up Work |  |  | WO No. | Status
Section | Number of Breakdown Jobcards | Problem / Cause Remedy Completed | Number of 5Y Required | Number of 5Y Completed | % Compliance (P/C/R) | % Compliance (5Y)
Mechanical Foreman | 64 | 0 |  | 0 | 0%
Drill Shop Foreman | 78 | 0 |  | 0 | 0%
Electrical Foreman | 6 | 0 |  | 0 | 0%
Fitter Foreman | 0 | 0 |  | 0
Boilermaker Foreman | 6 | 1 |  | 0 | 16.67%
Utility Vehicle Foreman | 5 | 0 |  | 0 | 0%

## Weekly report
Weekly Summary Report
Shaft N3 | [6 empty] | Plan YTD | Actual YTD | Plan MTD | Actual MTD | MTD Variance
[6 empty] | ROM | 1204982 | 1083588 | 72541 | 60310 | -12231
Week - Date | 2026-02-06 | To | 2026-02-12 |  |  | Product | 1101710 | 996655 | 59866 | 49230 | -10636
Safety
| YTD | No Week | Remarks
Minor Treatment Case | 15 | 0
Lost Time Injury | 3 | 0
Property Damage | 54 | 0
Incidents Reported | 2 | 0
Labour
| Plan | Actual | Leave | Not Specified | % AT Work |  | Remarks
Fri | 221 | 157 | 32 | 2 | 71%
Mon | 221 | 183 | 21 | 0 | 83%
Tues | 221 | 183 | 18 | 0 | 85%
Wed | 221 | 187 | 161 | 0 | 83%
Thurs | 221 | 184 | 16 | 0 | 62%
42
Remarks
COST By ELEMENT | MONTH ACTUAL | MONTH BUDGET | MONTH VAR | YTD ACTUAL | YTD BUDGET | YTD VAR
Labour Cost | 119423685.95 | 139522448.15 | 20098762.2 | 907699686.89 | 1004818384 | 97118697.11
Overtime | 6517101.92 | 5535760.8 | -981341.12 | 72481573.3 | 45268864.74 | -27212708.56
Incentive Provision | 30343878.73 | 30361798.27 | 17919.54 | 119746633.75 | 212532587.89 | 92785954.14
Stores | 36106805.68 | 47487725.81 | 11380920.13 | 339107813.65 | 355941087.22 | 16833273.57
Major Repairs | 21086887.8 | 24878116 | 3791228.2 | 144513434.73 | 177633480.52 | 33120045.79
Water | 2188638.38 | 1572068.14 | -616570.24 | 11123189.58 | 10903052.96 | -220136.62
Power | 26782014.52 | 24117764.91 | -2664249.61 | 209326624.25 | 200168981.95 | -9157642.3
Contractors | 37794908.24 | 27558623.97 | -10236284.27 | 172765526.07 | 190685135.3 | 17919609.23
Other Cost | 9594773.72 | 28301990.79 | 18707217.07 | 155891467.33 | 199532880.39 | 43641413.06
TOTAL | 289838694.94 | 329336296.84 | 39497601.9 | 2132655949.55 | 2397484454.97 | 264828505.42
0 |  |  |  |  | 0 | 0 | Remarks
Plant:Production |  |  |  |  | X
Mechanics: Production |  |  |  |  | X
Drills: Production |  |  |  |  | X
Electricians: Production |  |  |  |  | X
Boilermakers: Production |  |  |  |  | X
BEV : Production |  |  |  |  | X
Utility: Production |  |  |  |  | X
| Fri | Mon | Tue | Wed | Thu | Ave |  | List breakdowns that impacted availabilities
HD | 90% | 86% | 89% | 89% | 92% | 89.2%
RT | 89% | 95% | 97% | 88% | 73% | 88.4%
SR | 91% | 98% | 97% | 87% | 89% | 92.4%
DT Diesel | 85% | 77% | 75% | 76% | 74% | 77.4% | DT145 Gears Faulty,DT148 Aircon/Mainswitch,
FL Diesel | 58% | 64% | 59% | 58% | 63% | 60.4% | FL101 Steering Problem, FL103 not Starting, Aircon and Tagbox, FL90 Comms Error
DT batteries | 78% | 78% | 79% | 85% | 74% | 78.8% | DT171 A Frame,DT146 Isoaltor faulty,DT149 Invertor Error,DT162 Batt Overheat
FL Batteries | 83% | 81% | 90% | 81% | 94% | 85.8%
Average | [5 empty] | 81.77%
TMM Status SOS (Friday Morning) :
| Available | Plan | List the equipment on breakdown and reason
HD
RT
DT
FL
SR
Charge up UV`s
RORO/Flat deck UV`s
Weekly Primary TMM Maintenance Overview
Type | Plan | Actual | % | List detail if a service was missed | [5 empty] | No of Maintenance Over inspections
[10 empty] | Supervisor | Engineer / GES
FL | 5 | 2 | 40%
DT | 8 | 8 | 100%
FL BEV | 3 | 3 | 100%
DT BEV | 0 | 0 | #DIV/0!
HD | 4 | 4 | 100%
RT | 5 | 3 | 60%
SR | 4 | 4 | 100%
UV Emulsion Units | 0 | 0 | #DIV/0!
Support Equipment | 3 | 3 | 100%
Long Standing TMM Overview
Type | Breakdown |  |  | Status | [5 empty] | Commitment

## Weekly service schedule (hidden)
Asset Care Service Compliance
| Week: | 2023-01-16 | to | 2023-01-22
| 2023-01-16 | 2023-01-17 | 2023-01-18 | 2023-01-19 | 2023-01-20 | 2023-01-21 | 2023-01-22
Equipment type | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
DT |  | DT0126(1399983-250Hrs) |  | DT0127
1 x Sampels & Drain Engine
|  | 1385825-CAS |  | 1385826-CAS
FL
DZ/GD | GD0011 (1382776 - 500hrs) |  |  | FL0090(1389647-1000Hrs)
| Engine - Sample & Drain |  |  | Engine - Sample & Drain
| Transmission - Sample |  |  | Transmission - Sample & Drain
| Hydraulic - Sample |  |  | Hydraulic - Sample
| Tandem LH & RH - Sample |  |  | Axle x 2 & Final Drive x 4 - Sample & Drain
1385841-CAS
HD | HD0056 | HD0055 | HD0054 | HD0052
1385582-CAS
RT | RT0041 | RT0039 | RT0037 | RT0035 | RT0034
SR |  |  | SR0030(1383147-3Mnthly Service)
Support Vehicles-UV,CR,FT,BB |  |  |  | UV0079(1338475-500Hrs) | UV0074(1375287-250Hrs)
|  |  |  | Engine - Sample & Drain | 1 x Sampels & Drain Engine
Transmission - Sample
Hydraulic - Sample
Axle x 2 & Final Drive x 4 - Sample
Support Vehicles-LDVs | LD0556(1380299-LC 79 Mech Service) | LD0571(LC 79 Mech Service) | LD0569(1380249-LC 79 Mech Service)
| 1 x Sampels & Drain Engine | 1 x Sampels & Drain Engine | 1 x Sampels & Drain Engine
| 1385853-CAS | 1385815-CAS | 1400045-CAS
Maintenance Planner: |  | Maintenance Planner: |  | MO(SE) :
Foreman(Mechanic): |  | Production Engineer: |  | MO(Load & Haul) :
Foreman(Hyd Fiiter): |  | GES TMM: |  | MO(North) :
Foreman(Utility Vehicles): |  | GES Plant: |  | MO(Central) :
Foreman(Services): |  | Foreman (BEV) |  | MO:(SWD)

## Compliance Report
Weekly Asset Care Compliance Report Nchwaning III
Week Ending |  |  | 2026-02-12
Shaft / Area |  |  | Nch III U/G
Weekly Maintenance Schedule Compliance
Fleet / Equipment |  |  | Planned |  | Actual |  | Schedule Compliance |  | Target |  | Comment
FL(Diesel) | [8 empty] | 95%
DT(Diesel) |  |  | 2 |  | 2 |  | 100% |  | 95%
FL BEV |  |  | 1 |  | 1 |  | 100% |  | 95%
DT BEV |  |  | 3 |  | 2 |  | 66.67% |  | 95% |  | DT0171 on breakdown
HD |  |  | 5 |  | 5 |  | 100% |  | 95%
RT |  |  | 5 |  | 5 |  | 100% |  | 95%
SR | [8 empty] | 95%
UV Emulsion Units | [8 empty] | 95%
Support Equip. Diesel Foreman | [8 empty] | 95%
Support Equip Utility Foreman |  |  | 5 |  | 4 |  | 80% |  | 95%
BEV Batt |  |  | 5 |  | 5 |  | 100% |  | 95%
Weekly Quality Service Report
|  | Mining | [6 empty] | Engineering
Schedule Date | TMM Unit Number | Actual Time Available In Workshop - < 7:00 AM |  | 07:00 AM - 50% 08:00 AM - 25% 09:00 AM - 0% |  | Machine Clean for Maintenance | No - 0% Yes - 50% | 40.79% | Pre inspection & Operator Engagement - 3 Days Before Service Done |  | No - 0% Yes - 25% | Actual Service Duration - Plan 6 Hours | 6Hrs - 50% 5Hrs - 40% 4Hrs - 30% 3Hrs - 20% 2Hrs - 10% 1Hrs - 0% | Machine Tested and Over Inspected by Supervisor |  | No - 0% Yes - 25% | 97.37% |  | Time and Date to first Breakdown | Any Damages Observed
09/02/2026 | DT0162 | 7:00 |  | 50% |  | Yes | 50% | 100% | Yes |  | 25% | 5 | 40% | Yes |  | 25% | 90%
06/02/2026 | LDO604 | 8:00 |  | 25% |  | Yes | 50% | 75% | Yes |  | 25% | 6 | 50% | Yes |  | 25% | 100%
09/02/2026 | LDO606 | 7:00 |  | 50% |  | Yes | 50% | 100% | Yes |  | 25% | 6 | 50% | Yes |  | 25% | 100%
10/02/2026 | LD0608 | 7:00 |  | 50% |  | Yes | 50% | 100% | Yes |  | 25% | 6 | 50% | Yes |  | 25% | 100%
11/02/2026 | LD0609 | 8:00 |  | 25% |  | Yes | 50% | 75% | Yes |  | 25% | 6 | 50% | Yes |  | 25% | 100%
11/02/2026 | FL0012 | 7:00 |  | 50% |  | NO | 0% | 50% | Yes |  | 25% | 6 | 50% | Yes |  | 25% | 100%
12/02/2026 | DT0149 | 7:00 |  | 50% |  | NO | 0% | 50% | Yes |  | 25% | 6 | 50% | Yes |  | 25% | 100%
11/02/2026 | DT0160 | 8:00 |  | 25% |  | NO | 0% | 25% | YES |  | 25% | 6 | 50% | YES |  | 25% | 100%
12/02/2026 | DT0154 | 8:00 |  | 25% |  | NO | 0% | 25% | YES |  | 25% | 6 | 50% | YES |  | 25% | 100%
06/02/2026 | HD0052 | 8:00 |  | 25% |  | NO | 0% | 25% | YES |  | 25% | 6 | 50% | YES |  | 25% | 100%
06/02/2026 | RT0025 | 8:00 |  | 25% |  | NO | 0% | 25% | YES |  | 25% | 6 | 50% | YES |  | 25% | 100%
09/02/2026 | HD0055 | 9:00 |  | 0% |  | NO | 0% | 0% | YES |  | 25% | 5 | 40% | YES |  | 25% | 90%
09/02/2026 | RT0044 | 8:00 |  | 25% |  | NO | 0% | 25% | YES |  | 25% | 6 | 50% | YES |  | 25% | 100%
10/02/2026 | HD0056 | 10:00 |  | 0% |  | NO | 0% | 0% | YES |  | 25% | 4 | 30% | YES |  | 25% | 80%
10/02/2026 | RT0047 | 8:00 |  | 25% |  | NO | 0% | 25% | YES |  | 25% | 6 | 50% | YES |  | 25% | 100%
11/02/2026 | HD0057 | 8:00 |  | 25% |  | NO | 0% | 25% | YES |  | 25% | 6 | 50% | YES |  | 25% | 100%
11/02/2026 | RT0048 | 8:00 |  | 25% |  | NO | 0% | 25% | YES |  | 25% | 6 | 50% | YES |  | 25% | 100%
12/02/2026 | HD0058 | 8:00 |  | 25% |  | NO | 0% | 25% | YES |  | 25% | 6 | 50% | YES |  | 25% | 100%
12/02/2026 | RT0049 | 9:15 |  | 0% |  | NO | 0% | 0% | YES |  | 25% | 5 | 40% | YES |  | 25% | 90%
Weekly Filtration Compliance |  |  |  |  | Oil Filtration
|  | Planned |  | Actual
FL
DT
FL BEV
DT BEV
HD
RT
ISO Standard |  |  | Equipment |  | Oil type |  |  | Start reading |  | End Reading |  | Comments
Azola: 21/18/15
15W40: 21/18/15
ACX: 21/18/15
85W140: 20/19/17
Condition monitoring / Oil samples
Fleet / Equipment |  | Engine |  | Transmission / Gearbox |  | Hydraulic / Transformer |  | Axle |  | Gear Drop Box |  | Final Drive |  |  |  | Sample Paperwork Confirmation
|  | Plan | Received | Plan | Received | Plan | Received | Plan | Received | Plan | Received | Plan | Received | % Compliance |  | Total Sample Paperwork to Check |  | Paperwork Correct |  | Paperwork Incorrect | Urgent Oil Samples | Reasons for Non-Compliance
FL | [15 empty] | 0
DT |  | 2 | 2 | [10 empty] | 100% |  | 2
FL BEV |  |  |  | 1 | 1 | 1 | 1 | 2 | 2 |  |  | 4 | 4 | 100% |  | 8
DT BEV | [9 empty] | 2 | 2 |  |  | 100% |  | 2
HD | [15 empty] | 0
RT | [15 empty] | 0
SR | [15 empty] | 0
UV Emulsion Unites | [15 empty] | 0
Support Equipment |  | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 80% |  | 4
Plant | [15 empty] | 0
Over Inspections
Inspector |  | Planned Over-Inspections |  | Total Number of Inspections Completed |  | Corrective Work |  | WO Number |  | % Completed
Mech Foreman(Fortune) |  | 8 |  | 7 | [5 empty] | 87.5%
Mech Foreman(De Wee)
Hyd Drill Foreman |  | 3 |  | 3 | [5 empty] | 100%
Utility Vehicle Foreman
Electrical Foreman
Boilermaker
Plant Foreman |  | 3 |  | 3 | [5 empty] | 100%
GES TMM
GES Plant & BEV TMM
Engineer
BEV Foreman |  | 4 |  | 4 | [5 empty] | 100%
Equipment ID |  | Date of Inspection |  | Inspection Performed by |  | Findings and Defects Completed | [5 empty] | Additional Follow-up Work | [5 empty] | WO No. |  | Status
Mechanic Foreman1(Fortune)
UV0126 |  | 2026-02-09 |  | TSHEPISO |  | Strata repairs, replaced interface module & commisioning | [13 empty] | In Order
UV0122 |  | 2026-02-09 |  | KENAME |  | Fit rear axle | [13 empty] | Done
UV0112 |  | 2026-02-10 |  | MALEBOGO |  | Replace amber lights & Reverse hooter | [13 empty] | Done
UV0125 |  | 2026-02-10 |  | THABANG |  | Replace front axle | [5 empty] | Rear axle to be replaced | [7 empty] | Done
UV0124 |  | 2026-02-11 |  | MEI |  | Replace hyd fitting on hyd tank, damaged | [13 empty] | Done
UV0132 |  | 2026-02-11 |  | MAMOGOBO |  | Repair wiring on starting | [13 empty] | Done
UV0135 |  | 2026-02-12 |  | KENAME |  | Secure centre bearing bolts & replace grease pipe
UV0131 |  | 2026-02-10 |  |  |  | Not in for inspection
Equipment ID |  | Date of Inspection |  | Inspection Performed by |  | Findings and Defects Completed | [5 empty] | Additional Follow-up Work | [5 empty] | WO No. |  | Status
Mechanic Foreman2(De Wee)
Equipment ID |  | Date of Inspection |  | Inspection Performed by |  | Findings and Defects Completed | [5 empty] | Additional Follow-up Work | [5 empty] | WO No. |  | Status
Hyd Drill Foreman
RT0025 |  | 2026-02-06 |  | JOHANNES |  | NONE | [5 empty] | NONE | [7 empty] | In Order
HD0052 |  | 2026-02-06 |  | JOHANNES |  | AIRCON PUMP MOUNTINGS | [5 empty] | NONE | [7 empty] | In Order
RT0044 |  | 2026-02-10 |  | JOHANNES |  | FEEDMOTOR SPLINES | [5 empty] | HOSES | [7 empty] | In Progress
Equipment ID |  | Date of Inspection |  | Inspection Performed by |  | Findings and Defects Completed | [5 empty] | Additional Follow-up Work | [5 empty] | WO No. |  | Status
Utility Vehicle Foreman
LD0604 |  | 2026-02-06 |  | Tshepo |  | I.O | [13 empty] | In Order
LD0606 |  | 2026-02-09 |  | Tshepo |  | I.O | [13 empty] | In Order
LD0608 |  | 2026-02-10 |  | Tshepo |  | Door handle / Broken Shocks | [13 empty] | In Order
LD0609 |  | 2026-02-11 |  | Tshepo |  | I.O | [13 empty] | In Order
Equipment ID |  | Date of Inspection |  | Inspection Performed by |  | Findings and Defects Completed | [5 empty] | Additional Follow-up Work | [5 empty] | WO No. |  | Status
Electrical Foreman
Equipment ID |  | Date of Inspection |  | Inspection Performed by |  | Findings and Defects Completed | [5 empty] | Additional Follow-up Work | [5 empty] | WO No. |  | Status
Boilermaker
FEL0099 |  | 2026-02-07 |  | S Olyn |  | Half Arrows worn | [5 empty] | Machine Failed to Start | [7 empty] | Done
55CV01 Screen |  | 2026-02-11 |  | S Olyn |  | Deflector plate Worn | [5 empty] | Fabricated and installed new Plate | [7 empty] | Done
Equipment ID |  | Date of Inspection |  | Inspection Performed by |  | Findings and Defects Completed | [5 empty] | Additional Follow-up Work | [5 empty] | WO No. |  | Status
Plant Foreman
Tripper conveyor |  | 2026-02-09 |  | M. Jacobs |  | Mechanical joint to be splice | [13 empty] | In Progress
CP0222 |  | 2026-02-10 |  | M. Jacobs |  | Inspect | [13 empty] | In Order
Crusher sat 1 |  | 2026-02-12 |  | M. Jacobs |  | Crusher blocked | [5 empty] | Open crusher | [7 empty] | In Order
Equipment ID |  | Date of Inspection |  | Inspection Performed by |  | Findings and Defects Completed | [5 empty] | Additional Follow-up Work | [5 empty] | WO No. |  | Status
BEV Foreman
FL0098 |  | 2026-02-06 |  | Itumeleng |  | Accumulators loose, needs to be tighten. | [13 empty] | Done
DT0149 |  | 2026-02-06 |  | Wimpie |  | Tag box was bridge, is now unbridge. | [13 empty] | Done
FL0112 |  | 2026-02-11 |  | Wimpie |  | Fire extinguisher was damaged, is replaced. | [13 empty] | Done
DT0149 |  | 2026-02-12 |  | Wimpie |  | I/O | [13 empty] | In Order
Equipment ID |  | Date of Inspection |  | Inspection Performed by |  | Findings and Defects Completed | [5 empty] | Additional Follow-up Work | [5 empty] | WO No. |  | Status
GES Plant & BEV TMM
Equipment ID |  | Date of Inspection |  | Inspection Performed by |  | Findings and Defects Completed | [5 empty] | Additional Follow-up Work | [5 empty] | WO No. |  | Status
GES TMM
Equipment ID |  | Date of Inspection |  | Inspection Performed by |  | Findings and Defects Completed | [5 empty] | Additional Follow-up Work | [5 empty] | WO No. |  | Status
Engineer
Breakdown Work Orders P/C/R and 5Y's Compliance
Section |  |  | Number of Breakdown Job Cards Created |  | Number of Breakdown Job Cards Closed (SO) |  | Problem / Cause Remedy Completed |  | Number of 5Y Required Longer Than 1HR |  | Number of 5Y Completed Longer Than 1HR |  | % Compliance (P/C/R) |  | % Compliance (5Y)
Boilermaker Foreman |  |  | 9 |  | 0 |  | 0 |  | 0 |  | 0
Electrical Foreman |  |  | 10 |  | 0 |  | 0 |  | 0 |  | 0
Mechanical Foreman1(De Wee) |  |  | 37 |  | 0 |  | 0 |  | 0 |  | 0
Mechanical Foreman2(Fortune) |  |  | 56 |  | 0 |  | 0 |  | 0 |  | 0
Plant Fitter Foreman |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Drill Shop Foreman |  |  | 131 |  | 0 |  | 0 |  | 0 |  | 0
Utility Vehicle Foreman |  |  | 48 |  | 4 |  | 0 |  | 1 |  | 0 |  | 0% |  | 0%
BEV Foreman |  |  | 31 |  | 0 |  | 0 |  | 0 |  | 0
Work Order Backlog |  |  |  | 2025-07-01 |  |  |  | 2026-02-12
PERIOD | SCHED | Complete (#SO, #ST) | Cancel (#SP, #ST) | Wait Parts (#SB,#SH,#SI,#SK,#SL) | % Completed | Open
| 32403 | 30075 | 2159 | 1 | 92.82%
202502 | 3854 | 3440 | 391 | 0 | 89.26% | 23
202501 | 4264 | 3752 | 480 | 1 | 87.99% | 31
202412 | 3623 | 3430 | 180 | 0 | 94.67% | 13
202411 | 4053 | 3637 | 394 | 0 | 89.74% | 22
202410 | 4286 | 3998 | 272 | 0 | 93.28% | 16
202409 | 3933 | 3737 | 180 | 0 | 95.02% | 16
202408 | 4216 | 4089 | 108 | 0 | 96.99% | 19
202407 | 4174 | 3992 | 154 | 0 | 95.64% | 28
0
0
0
0
Work orders in 'S' status |  |  |  | 2025-07-01 |  |  |  | 2026-02-12
31101 | MINE MANAGER |  |  | 2
31105 | MINE OVERSEER SERVICES |  |  | 1
31135 | SHIFT BOSS 1 CONSTRUCTION |  |  | 40
31170 | FOREMAN BIT SHOP NCH III |  |  | 259
33302 | SECTION ENGINEER NCH III |  |  | 0
33310 | GES TMM |  |  | 0
33311 | GES PLANT |  |  | 1
33320 | PLANNER |  |  | 0
33332 | FOREMAN BOILERMAKER |  |  | 0
33334 | FOREMAN ELECTRICAL |  |  | 33
33337 | FOREMAN MECHANICAL(1) |  |  | 75
33338 | FOREMAN PLANT |  |  | 0
33341 | FOREMAN DRILL SHOP |  |  | 90
33342 | FOREMAN UTILITY |  |  | 71
33344 | FOREMAN BEV |  |  | 48
33345 | FOREMAN MECHANICAL(2) |  |  | 55
Note on U42: Rahab Makolomakwa: Record time of first breakdown after service as instructed by Engineering Manager.
Note on R100: Foreman Complete Sample Paperwork Compliance For All Samples taken

## Service Schedule
Asset Care Maintenance
| Week: | 2026-02-06 | to |  | 12 Februay 2026
| 2026-02-06 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12
Equipment Type | Friday | Monday | Tuesday | Wednesday | Thursday
DT | DT0171 | DT0162 - 1927589 | DT0154 - 1927591 | DT0160 - 1927594 | DT0149 - 1927598
| N3 CAS 3Monthly Inspection |  |  | N3 CAS 3Monthly Inspection | N3 CAS 3Monthly Inspection
|  | N3 MT42B Mech 250Hr Maintenanc | AD30 250 HOURS SERVICE | AD30 250 HOURS SERVICE | N3 MT42B Mech 500Hr Maintenanc
| N3 MT42B Mech Daily Inspection | N3 MT42B Mech Daily Inspection | N3 DT Diesel Auto Electrician | N3 DT Diesel Auto Electrician | N3 MT42B Mech Daily Inspection
| N3 MT42B Load Box / Chassis /A | N3 MT42B Load Box / Chassis /A | D.T BUCKET/CHASSIS/ARTIC Insp | D.T BUCKET/CHASSIS/ARTIC Insp | N3 MT42B Load Box / Chassis /A
FL/DZ/GD |  |  | FL0112 - 1927602 | FL0121
|  |  | N3 CAS 3Monthly Inspection | N3 CAS 3Monthly Inspection
N3 ST14B Mech 2000Hrs Maintena
|  |  | N3 ST14B Mech Daily Inspection | Loader ST14 Mech Wk. Insp
|  |  | N3 ST14B Bucket / Chassis /Art | FEL Ins BCKT/S-BLOCK/ARTIC Wk
HD | HD0051 | HD0052 | HD0055 | HD0056 | HD0057
| N3 CAS 3Monthly Inspection | N3 CAS 3Monthly Inspection |  |  | N3 CAS 3Monthly Inspection
| N3 HD Auto Electrician Maint | N3 HD Auto Electrician Maint | N3 HD Auto Electrician Maint | N3 HD Auto Electrician Maint | N3 HD Auto Electrician Maint
| N3 Hyd Drill 2Wk Diff Ins | N3 Hyd Drill 2Wk Diff Ins | N3 Hyd Drill 2Wk Diff Ins | N3 Hyd Drill 2Wk Diff Ins | N3 Hyd Drill 2Wk Diff Ins
| Hyd Drill El Wk Main | Hyd Drill El Wk Main | Hyd Drill El Wk Main | Hyd Drill El Wk Main | Hyd Drill El Wk Main
| S2 WEEKLY MECH MAINTENANCE | S2 WEEKLY MECH MAINTENANCE | S2 WEEKLY MECH MAINTENANCE | S2 WEEKLY MECH MAINTENANCE | S2 WEEKLY MECH MAINTENANCE
RT | RT0058 | RT0025 | RT0044 | RT0047 | RT0048
| N3 CAS 3Monthly Inspection | N3 CAS 3Monthly Inspection | N3 CAS 3Monthly Inspection | N3 CAS 3Monthly Inspection
| N3 RT Auto Electrician Maint | N3 RT Auto Electrician Maint | N3 RT Auto Electrician Maint | N3 RT Auto Electrician Maint | N3 RT Auto Electrician Maint
| N3 Hyd Drill 2Wk Diff Ins | N3 Hyd Drill 2Wk Diff Ins | N3 Hyd Drill 2Wk Diff Ins | N3 Hyd Drill 2Wk Diff Ins | N3 Hyd Drill 2Wk Diff Ins
| N3 Hyd Drill El 2Wk Main | N3 Hyd Drill El 2Wk Main | N3 Hyd Drill El 2Wk Main | N3 Hyd Drill El 2Wk Main | N3 Hyd Drill El 2Wk Main
| N3 Roofbolter Mech 2Wk. Maint | N3 Roofbolter Mech 2Wk. Maint | N3 Roofbolter Mech 2Wk. Maint | N3 Roofbolter Mech 2Wk. Maint | N3 Roofbolter Mech 2Wk. Maint
SR | SR0038 - 1924092 | SR0039 - 1927534 | SR0043 - 1927535 | SR0044 - 1927536 | SR0024 - 1927537
| N3 CAS 3Monthly Inspection | N3 CAS 3Monthly Inspection | N3 CAS 3Monthly Inspection | N3 CAS 3Monthly Inspection | N3 CAS 3Monthly Inspection
| N3 Scaler 125HR Service | N3 Scaler 125HR Service | N3 Scaler 125HR Service | N3 Scaler 125HR Service | N3 Scaler 125HR Service
| N3 Scaler Auto Electrician | N3 Scaler Auto Electrician | N3 Scaler Auto Electrician | N3 Scaler Auto Electrician | N3 Scaler Auto Electrician
| Scaler Mech Wk. Insp | Scaler Mech Wk. Insp | Scaler Mech Wk. Insp | Scaler Mech Wk. Insp | Scaler Mech Wk. Insp
Emulsion Charging Units |  | UV0126 | UV0131 | UV0134 | UV0135
|  | N3 CAS 3Monthly Inspection | N3 CAS 3Monthly Inspection | N3 CAS 3Monthly Inspection | N3 CAS 3Monthly Inspection
|  | N3 Support TMM Auto Electric | N3 Support TMM Auto Electric | N3 Support TMM Auto Electric | N3 Support TMM Auto Electric
|  | UV 80 DAILY INSP EMULSION | UV 80 DAILY INSP EMULSION | UV 80 DAILY INSP EMULSION | UV 80 DAILY INSP EMULSION
Scissor Lift Units |  | UV0107 | UV0112 | UV0122 | UV0132 - 1927531
|  | N3 CAS 3Monthly Inspection |  | N3 CAS 3Monthly Inspection | N3 CAS 3Monthly Inspection
U/Veh Mech 500 Hrs Service
|  | N3 Support TMM Auto Electric | N3 Support TMM Auto Electric | N3 Support TMM Auto Electric | N3 Support TMM Auto Electric
|  | UV Aard 60/80 daily insp | Utility Vehicle Mech Wk. Insp | Utility Vehicle Mech Wk. Insp | UV Aard 60/80 daily insp
Support Vehicles - BB, FT, LD, UV,CR | LD0604 - 1917253 | LD0606 - 1915950 | LD0608 - 1919405 | LD0609 - 1919614 | LD0611 - 1919615
| Engine - Sample & Drain | Engine - Sample & Drain | Engine - Sample & Drain | Engine - Sample & Drain | Engine - Sample & Drain
| N3 CAS 3Monthly Inspection | N3 CAS 3Monthly Inspection | N3 CAS 3Monthly Inspection | N3 CAS 3Monthly Inspection | N3 CAS 3Monthly Inspection
| LC 79 Mech Service | LC 79 Mech Service | LC 79 Mech Service | LC 79 Mech Service | LC 79 Mech Service
| N3 Support TMM Auto Electric | N3 Support TMM Auto Electric | N3 Support TMM Auto Electric | N3 Support TMM Auto Electric | N3 Support TMM Auto Electric
Battery | VPY-00041(BY0029) - 1926503 | VPX00016 (BY0008) - 1928266 | VPY00048 (BY0011) - 1928272 | VPX00017 (BY0005) - 1928273 | VPY00049 (BY0021) - 1928274
| TMS Coolant hoses checks | TMS Coolant hoses checks | TMS Coolant hoses checks | TMS Coolant hoses checks | TMS Coolant hoses checks

## Weekly Oil Report
Row Labels | Sum of Azolla ZS 68 | Sum of Rubia TIR 7400
DT0118 | 0 | 212.8 | Hydr hoses change
DT0119 | 0 | 62.3
DT0131 | 0 | 72.3
DT0154 | 0 | 40.8
DT0160 | 0 | 0
DT0161 | 0 | 62.3
FL0056 | 0 | 11.7
FL0080 | 0 | 27
FL0091 | 0 | 18.3
HD0050 | 64.9 | 0
HD0052 | 40.1 | 0
HD0069 | 72 | 0
RT0051 | 26.1 | 0
RT0052 | 28.8 | 0
RT0054 | 21 | 0
SR0026 | 28.9 | 12.2
SR0030 | 140 | 6.2
SR0038 | 122.4 | 0 | Replaced engine & suction hoses
SR0039 | 14.5 | 1.7
UV0074 | 0 | 0.4
UV0091 | 23.3 | 0
UV0126 | 0.4 | 8.1
Grand Total | 582.4 | 536.1

## Hydraulic pipe report
Row Labels | Abrasion | Fitting Damaged | Hose Burst | Hose Damaged | Rock Fall | Spare Hose | Wear & Tear | Service | Grand Total
DT |  | 1 | [5 empty] | 2 | 3
FL |  |  | 2 |  |  |  | 1 |  | 3
HD | 88 | 12 |  | 7 |  |  | 2 | 14 | 123
HH | [8 empty] | 0
LD | 1 | [7 empty] | 1
RT | 48 | 14 | 2 |  |  |  |  | 6 | 70
SR | 9 | [6 empty] | 5 | 14
Grand Total | 146 | 27 | 4 | 7 | 0 | 0 | 3 | 27 | 214

## Block Chute Report
Daily Block Chute Tracker
Date | Time Taken to unblock | Belt feed 01 | Belt feed 02 | Raisebelt | Tripper car | 55cv01 | 55cv02 | 55cv03 | 60cv01 | 60cv02 | 65cv01 | 65cv02 | Silo bottom | Decline
2026-02-01 | No blockage
2026-02-02 | [8 empty] | x
2026-02-03 | No blockage
2026-02-04 | No blockage
2026-02-05 | [12 empty] | x
2026-02-06 | No blockage
2026-02-07 | No blockage
2026-02-08 | [11 empty] | x
2026-02-09 | [8 empty] | x
2026-02-10 | [10 empty] | x
2026-02-11 | No blockage
2026-02-12 | No blockage
2026-02-13
2026-02-14
2026-02-15
2026-02-16
2026-02-17
2026-02-18
2026-02-19
2026-02-20
2026-02-21
2026-02-22
2026-02-23
2026-02-24
2026-02-25
2026-02-26
2026-02-27
2026-02-28
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 1 | 0

## Wash Machine Report
Washing of Machinery Week 12 Feb 2026
Friday |  | Monday |  | Tuesday |  | Wednesday |  | Thursday
06/02/2026 | Actual | 09/01/2026 | Actual | 10/02/2026 | Actual | 11/02/2026 | Actual | 12/02/2026 | Actual
DT0171 | Not In | DT0162 | Not In | DT0154 | Not Washed | DT0160 | Not Washed | DT0149 | Not In
HD0051 | Not In | HD0052 | Not In | FL0112 | Not In | FL0121 | Not Washed | HD0057 | Not In
RT0058 | Not In | RT0025 | Not In | HD0055 | Not In | HD0056 | Not In | RT0048 | Not In
SR0038 | Breakdown | SR0039 | Not Washed | RT0044 | Not Washed | RT0047 | Not In | SR0024 | Not Washed
LDO604 | Not Washed | UV0126 | Not Washed | SR0043 | Not Washed | SR0044 | Not In | UV0135 | Not Washed
|  | UV0107 | Breakdown | UV0131 | Not Washed | UV0134 | Not Washed | UV0132 | Not Washed
|  | LDO606 | Not Washed | UV0112 | Not Washed | UV0122 | Not Washed | LDO611 | Not Washed
Not schedulled machinery.
|  |  |  | LDO0615 | Washed |  |  | DT0149 | Washed
|  |  |  | LDO0570 | Washed |  |  | FL0112 | Washed
|  |  |  | LDO614 | Washed
|  |  |  | LDO645 | Washed
Total | 0 |  | 0 |  | 4 |  | 0 |  | 2
Washed | 6
Not Washed | 17
Not In | 13
Breakdown | 2
Monday 28/07/2025 |  | Tuesday 29/07/2025 |  | Wednesday 30/07/2025 |  | Thursday 31/07/2025 |  | Friday 01/08/2025
Drill Rigs washed by Hydraulic Presonnel.

## UGToyota & Fermel 06 Feb 26
06/02/2026 DAY SHIFT REPORT
No | Area / Owner | TMM No. | Description - EOS / Breakdown | Remaks /Comment | OEM Assistance Required / Waiting Parts |  | Total | Breakdown | Availability
1 | Plant Fitter | BB0002 | Available |  |  | Maverick Double cab | 9 | 2 | 77.78%
2 | Plant Fitter | BB0006 | Available |  |  | Toyota Landcruiser Minespec | 33 | 2 | 93.94%
3 | Tyre Bay | LD0272 | Available |  |  | Toyota Landcruiser | 2 | 0 | 100%
4 | Ambulance | LD0283 | Available |  |  | Toyota Hilux | 2 | 0 | 100%
5 | Exploisive | LD0319 | Available |  |  | Maverick Man lift | 4 | 0 | 100%
6 | BEV | LD0375 | Available |  |  | Placer dumper | 1 | 0 | 100%
7 | Training Center | LD0401 | Available |  |  | Maverick king Cab c/w Crane | 3 | 0 | 100%
8 | Boilermaker | LD0405 | Not Available | Engine commision( No comminication between engine and Machine) | No solution from Fermel(Deutz EMR4 upgrade to EMR5) | Maverick Single cab Jam Pot | 1 | 0 | 100%
9 | Itireleng | LD0409 | Available |  |  | Bird Machine | 1 | 1 | 0%
10 | Hyd Fitter | LD0413 | Available |  |  | Bob Cat | 2 | 0 | 100%
11 | Instrumentation | LD0421 | Available |  |  | Maverick King Cab NO Crane | 2 | 0 | 100%
12 | Geology | LD0422 | Available |  |  | ROROs | 5 | 1 | 80%
13 | Electricians | LD0445 | Available |  |  | TOTAL | 65 | 6 | 90.77%
14 | Plant Fitter | LD0452 | Available
15 | Hyd Fitter | LD0512 | Available
16 | Main West | LD0520 | Not Available | Strata - (SOS - 12:51)
17 | Hyd Fitter | LD0555 | Available
18 | Traimming | LD0556 | Available | Not accelerating - SOS - 11:00)
19 | Drill Shop | LD0568 | Available
20 | Electricians | LD0569 | Available
21 | Mechanics | LD0570 | Available
22 | X Cut | LD0571 | Available
23 | Central | LD0572 | Available
24 | Utility TMM | LD0573 | Available
25 | Construction | LD0574 | Available
26 | Security | LD0595 | Available
27 | Rock Engneering | LD0604 | Available
28 | Construction | LD0606 | Available
29 | Mechanics | LD0607 | Available
30 | Traimming | LD0608 | Available
31 | Hyd Fitter | LD0609 | Available
32 | Plant Fitter | LD0610 | Available
33 | Main West | LD0611 | Available
34 | Hyd Fitter | LD0612 | Available
35 | Construction | LD0613 | Available
36 | Mechanics | LD0614 | Available
37 | Boilermaker | LD0615 | Available
38 | Plant Fitter | LD0620 | Not Available | Strata (Surface decline & No acces to the gat, its locked ) - (SOS - EOS)
39 | Sim 2 | LD0622 | Available
40 | Training Center | LD0624 | Available
41 | Central | LD0625 | Not Available | Park brake button broken off - (SOS - EOS)
42 | Electricians | LD0626 | Available
43 | SWD | LD0627 | Available
44 | Manager | LD0628 | Available
45 | Drill Shop | LD0635 | Available
46 | Boilermaker | UV0071 | Available
47 | Sampling | UV0074 | Available
48 | Sampling | UV0075 | Available
49 | Logistics | UV0078 | Not Available | Rear axle - (SOS - EOS)
50 | Logistics | UV0079 | Available
51 | Logistics | UV0081 | Available
52 | Logistics | UV0082 | Available
53 | Logistics | UV0086 | Available | Outriggers mulfunctioning - (08:00 - 12:29)
54 | Plant Fitter | UV0088 | Available
55 | Hyd Fitter | UV0091 | Available | Lights - (12:27 - 13:56)
56 | Utility TMM | UV0094 | Available
57 | Survey | UV0100 | Available
58 | Survey | UV0101 | Available
59 | Sanitec | UV0103 | Available
60 | Logistics | UV0116 | Available
61 | Logistics | UV0045 | Not Available | Brakes locked @ NCH2 - (SOS - EOS)
62 | Mining | LD0646 | Available
63 | Electricians | LD0643 | Available | Brakes not realising - (09:00 - 10:57)
64 | Plant Fitter | LD0644 | Available
65 | BEV | LD0645 | Available
LABOUR
| Chargehand | 1/1
| Mech | 5/8 | X 1 annual leave
| Auto | 1/4 | x1 on sick leave untill April /x1 at training center as from last year / X1 Annual leave
| Semi skilled | 2/2

## UGToyota & Fermel 09 Feb 26
09/02/2026 DAY SHIFT REPORT
No | Area / Owner | TMM No. | Description - EOS / Breakdown | Remaks /Comment | OEM Assistance Required / Waiting Parts |  | Total | Breakdown | Availability
1 | Plant Fitter | BB0002 | Available |  |  | Maverick Double cab | 9 | 2 | 77.78%
2 | Plant Fitter | BB0006 | Available |  |  | Toyota Landcruiser Minespec | 33 | 1 | 96.97%
3 | Tyre Bay | LD0272 | Available |  |  | Toyota Landcruiser | 2 | 0 | 100%
4 | Ambulance | LD0283 | Available |  |  | Toyota Hilux | 2 | 0 | 100%
5 | Exploisive | LD0319 | Available |  |  | Maverick Man lift | 4 | 0 | 100%
6 | BEV | LD0375 | Available |  |  | Placer dumper | 1 | 0 | 100%
7 | Training Center | LD0401 | Available |  |  | Maverick king Cab c/w Crane | 3 | 0 | 100%
8 | Boilermaker | LD0405 | Not Available | Engine commision( No comminication between engine and Machine) | No solution from Fermel(Deutz EMR4 upgrade to EMR5) | Maverick Single cab Jam Pot | 1 | 0 | 100%
9 | Itireleng | LD0409 | Available |  |  | Bird Machine | 1 | 0 | 100%
10 | Hyd Fitter | LD0413 | Available |  |  | Bob Cat | 2 | 0 | 100%
11 | Instrumentation | LD0421 | Available |  |  | Maverick King Cab NO Crane | 2 | 0 | 100%
12 | Geology | LD0422 | Available |  |  | ROROs | 5 | 1 | 80%
13 | Electricians | LD0445 | Available |  |  | TOTAL | 65 | 4 | 93.85%
14 | Plant Fitter | LD0452 | Available | Overheating - (08:59 - EOS)
15 | Hyd Fitter | LD0512 | Available
16 | Main West | LD0520 | Available
17 | Hyd Fitter | LD0555 | Available
18 | Traimming | LD0556 | Available | Not Accelerating - (SOS - 11:09)
19 | Drill Shop | LD0568 | Available
20 | Electricians | LD0569 | Available
21 | Mechanics | LD0570 | Available
22 | X Cut | LD0571 | Available
23 | Central | LD0572 | Available | Not Accelerating - (SOS - 11:09)
24 | Utility TMM | LD0573 | Available | Oil drain plug threats are stripped out - (SOS - EOS)
25 | Construction | LD0574 | Available
26 | Security | LD0595 | Available
27 | Rock Engneering | LD0604 | Available
28 | Construction | LD0606 | Available
29 | Mechanics | LD0607 | Available
30 | Traimming | LD0608 | Available
31 | Hyd Fitter | LD0609 | Available
32 | Plant Fitter | LD0610 | Available
33 | Main West | LD0611 | Available
34 | Hyd Fitter | LD0612 | Available
35 | Construction | LD0613 | Available
36 | Mechanics | LD0614 | Available
37 | Boilermaker | LD0615 | Available
38 | Plant Fitter | LD0620 | Not Available | Strata (Surface decline & No acces to the gat, its locked ) - (SOS - EOS)
39 | Sim 2 | LD0622 | Available
40 | Training Center | LD0624 | Available
41 | Central | LD0625 | Available | Park brake button broken off - (SOS - 10:35)
42 | Electricians | LD0626 | Available
43 | SWD | LD0627 | Available
44 | Manager | LD0628 | Available
45 | Drill Shop | LD0635 | Available
46 | Boilermaker | UV0071 | Available
47 | Sampling | UV0074 | Available
48 | Sampling | UV0075 | Available
49 | Logistics | UV0078 | Not Available | Rear axle - (SOS - EOS)
50 | Logistics | UV0079 | Available
51 | Logistics | UV0081 | Available
52 | Logistics | UV0082 | Available
53 | Logistics | UV0086 | Available
54 | Plant Fitter | UV0088 | Available
55 | Hyd Fitter | UV0091 | Available
56 | Utility TMM | UV0094 | Available
57 | Survey | UV0100 | Available
58 | Survey | UV0101 | Available
59 | Sanitec | UV0103 | Available
60 | Logistics | UV0116 | Available
61 | Logistics | UV0045 | Not Available | Brakes locked @ NCH2 - (SOS - EOS)
62 | Mining | LD0646 | Available
63 | Electricians | LD0643 | Available
64 | Plant Fitter | LD0644 | Available
65 | BEV | LD0645 | Available
LABOUR
| Chargehand | 1/1
| Mech | 5/8 | X 1 annual leave
| Auto | 2/4 | x1 on sick leave untill April /x1 at training center as from last year
| Semi skilled | 2/2

## UGToyota & Fermel 10 Feb 26
10/2/2026 DAY SHIFT REPORT
No | Area / Owner | TMM No. | Description - EOS / Breakdown | Remaks /Comment | OEM Assistance Required / Waiting Parts |  | Total | Breakdown | Availability
1 | Plant Fitter | BB0002 | Available |  |  | Maverick Double cab | 9 | 2 | 77.78%
2 | Plant Fitter | BB0006 | Available |  |  | Toyota Landcruiser Minespec | 33 | 1 | 96.97%
3 | Tyre Bay | LD0272 | Available |  |  | Toyota Landcruiser | 2 | 0 | 100%
4 | Ambulance | LD0283 | Available |  |  | Toyota Hilux | 2 | 0 | 100%
5 | Exploisive | LD0319 | Available |  |  | Maverick Man lift | 4 | 0 | 100%
6 | BEV | LD0375 | Available |  |  | Placer dumper | 1 | 0 | 100%
7 | Training Center | LD0401 | Available |  |  | Maverick king Cab c/w Crane | 3 | 0 | 100%
8 | Boilermaker | LD0405 | Not Available | Engine commision( No comminication between engine and Machine) | No solution from Fermel(Deutz EMR4 upgrade to EMR5) | Maverick Single cab Jam Pot | 1 | 0 | 100%
9 | Itireleng | LD0409 | Available |  |  | Bird Machine | 1 | 0 | 100%
10 | Hyd Fitter | LD0413 | Available |  |  | Bob Cat | 2 | 0 | 100%
11 | Instrumentation | LD0421 | Available |  |  | Maverick King Cab NO Crane | 2 | 0 | 100%
12 | Geology | LD0422 | Available |  |  | ROROs | 5 | 1 | 80%
13 | Electricians | LD0445 | Available |  |  | TOTAL | 65 | 4 | 93.85%
14 | Plant Fitter | LD0452 | Not Available | Overheating - (SOS - EOS)
15 | Hyd Fitter | LD0512 | Available
16 | Main West | LD0520 | Available
17 | Hyd Fitter | LD0555 | Available
18 | Traimming | LD0556 | Available
19 | Drill Shop | LD0568 | Available
20 | Electricians | LD0569 | Available | Lights are not working - (10:43 - 14: 16)
21 | Mechanics | LD0570 | Available
22 | X Cut | LD0571 | Available
23 | Central | LD0572 | Available
24 | Utility TMM | LD0573 | Available
25 | Construction | LD0574 | Available
26 | Security | LD0595 | Available
27 | Rock Engneering | LD0604 | Available
28 | Construction | LD0606 | Available
29 | Mechanics | LD0607 | Available
30 | Traimming | LD0608 | Available
31 | Hyd Fitter | LD0609 | Available
32 | Plant Fitter | LD0610 | Available
33 | Main West | LD0611 | Available | Changing tyre - (08:13 - 08:33)
34 | Hyd Fitter | LD0612 | Available | Puncture - (09:54 - 11:37)
35 | Construction | LD0613 | Available
36 | Mechanics | LD0614 | Available
37 | Boilermaker | LD0615 | Available
38 | Plant Fitter | LD0620 | Not Available | Strata (Surface decline) - (SOS - EOS)
39 | Sim 2 | LD0622 | Available
40 | Training Center | LD0624 | Available
41 | Central | LD0625 | Available
42 | Electricians | LD0626 | Available
43 | SWD | LD0627 | Available | Rear axle guard loose & Lights not working - (SOS - 14:15)
44 | Manager | LD0628 | Available
45 | Drill Shop | LD0635 | Available
46 | Boilermaker | UV0071 | Available | Inclonometor - (12:26 - EOS)
47 | Sampling | UV0074 | Available
48 | Sampling | UV0075 | Available
49 | Logistics | UV0078 | Not Available | Brakes leaking(rear axle) - (SOS - EOS)
50 | Logistics | UV0079 | Available
51 | Logistics | UV0081 | Available
52 | Logistics | UV0082 | Available
53 | Logistics | UV0086 | Available
54 | Plant Fitter | UV0088 | Available
55 | Hyd Fitter | UV0091 | Available
56 | Utility TMM | UV0094 | Available
57 | Survey | UV0100 | Available
58 | Survey | UV0101 | Available
59 | Sanitec | UV0103 | Available
60 | Logistics | UV0116 | Available
61 | Logistics | UV0045 | Available
62 | Mining | LD0646 | Available
63 | Electricians | LD0643 | Available
64 | Plant Fitter | LD0644 | Available | Puncture - (11:26 - 13:58)
65 | BEV | LD0645 | Available
LABOUR
| Chargehand | 1
| Mech | 5/8 | X 1 annual leave
| Auto | 1/4 | x1 procedures / x1 sick leave /x1 at training center as from last year
| Semi skilled | 2/2

## UGToyota & Fermel 11 Feb 26
11/02/2026 DAY SHIFT REPORT
No | Area / Owner | TMM No. | Description - EOS / Breakdown | Remaks /Comment | OEM Assistance Required / Waiting Parts |  | Total | Breakdown | Availability
1 | Plant Fitter | BB0002 | Available |  |  | Maverick Double cab | 9 | 2 | 77.78%
2 | Plant Fitter | BB0006 | Available |  |  | Toyota Landcruiser Minespec | 33 | 1 | 96.97%
3 | Tyre Bay | LD0272 | Available |  |  | Toyota Landcruiser | 2 | 0 | 100%
4 | Ambulance | LD0283 | Available |  |  | Toyota Hilux | 2 | 0 | 100%
5 | Exploisive | LD0319 | Available |  |  | Maverick Man lift | 4 | 0 | 100%
6 | BEV | LD0375 | Available |  |  | Placer dumper | 1 | 0 | 100%
7 | Training Center | LD0401 | Available |  |  | Maverick king Cab c/w Crane | 3 | 0 | 100%
8 | Boilermaker | LD0405 | Not Available | Engine commision( No comminication between engine and Machine) | No solution from Fermel(Deutz EMR4 upgrade to EMR5) | Maverick Single cab Jam Pot | 1 | 0 | 100%
9 | Itireleng | LD0409 | Available |  |  | Bird Machine | 1 | 0 | 100%
10 | Hyd Fitter | LD0413 | Available |  |  | Bob Cat | 2 | 0 | 100%
11 | Instrumentation | LD0421 | Available |  |  | Maverick King Cab NO Crane | 2 | 0 | 100%
12 | Geology | LD0422 | Available |  |  | ROROs | 5 | 1 | 80%
13 | Electricians | LD0445 | Available |  |  | TOTAL | 65 | 4 | 93.85%
14 | Plant Fitter | LD0452 | Available
15 | Hyd Fitter | LD0512 | Available
16 | Main West | LD0520 | Not Available | Wiring - (SOS - EOS)
17 | Hyd Fitter | LD0555 | Available | Faulty lights - (14:18 - 15:30)
18 | Traimming | LD0556 | Available
19 | Drill Shop | LD0568 | Available
20 | Electricians | LD0569 | Available
21 | Mechanics | LD0570 | Available
22 | X Cut | LD0571 | Available
23 | Central | LD0572 | Available | No revs - (08:52 - 12:52)
24 | Utility TMM | LD0573 | Available
25 | Construction | LD0574 | Available
26 | Security | LD0595 | Available
27 | Rock Engneering | LD0604 | Available
28 | Construction | LD0606 | Available
29 | Mechanics | LD0607 | Available
30 | Traimming | LD0608 | Available
31 | Hyd Fitter | LD0609 | Maintenance
32 | Plant Fitter | LD0610 | Available
33 | Main West | LD0611 | Available
34 | Hyd Fitter | LD0612 | Available
35 | Construction | LD0613 | Available
36 | Mechanics | LD0614 | Available
37 | Boilermaker | LD0615 | Available
38 | Plant Fitter | LD0620 | Not Available | Strata (Surface decline) - (SOS - EOS)
39 | Sim 2 | LD0622 | Available
40 | Training Center | LD0624 | Available
41 | Central | LD0625 | Available
42 | Electricians | LD0626 | Available | No Revs - (EOS - 09:23) - No power supply to fuse box(11:50 - EOS)
43 | SWD | LD0627 | Available
44 | Manager | LD0628 | Available
45 | Drill Shop | LD0635 | Available
46 | Boilermaker | UV0071 | Available | Inclonometor - (SOS - 13:21)
47 | Sampling | UV0074 | Available
48 | Sampling | UV0075 | Available
49 | Logistics | UV0078 | Not Available | Propshaft - (SOS - EOS) | Ordered 06 Oct 2025 (No stock at fermel)
50 | Logistics | UV0079 | Available
51 | Logistics | UV0081 | Available
52 | Logistics | UV0082 | Available
53 | Logistics | UV0086 | Available
54 | Plant Fitter | UV0088 | Available
55 | Hyd Fitter | UV0091 | Available | Not switching on - (11:07 - EOS)
56 | Utility TMM | UV0094 | Available
57 | Survey | UV0100 | Available
58 | Survey | UV0101 | Available | Powerless - (09:21 - 10:26) Strata - (10:26 -
59 | Sanitec | UV0103 | Available
60 | Logistics | UV0116 | Available
61 | Logistics | UV0045 | Available
62 | Mining | LD0646 | Available
63 | Electricians | LD0643 | Available
64 | Plant Fitter | LD0644 | Available
65 | BEV | LD0645 | Available
LABOUR
| Chargehand | 1/1
| Mech | 5/8 | X 1 annual leave
| Auto | 2/4 | x1 sick leave /x1 at training center as from last year
| Semi skilled | 2/2

## UGToyota & Fermel 12 Feb 26
12/02/2026 DAY SHIFT REPORT
No | Area / Owner | TMM No. | Description - EOS / Breakdown | Remaks /Comment | OEM Assistance Required / Waiting Parts |  | Total | Breakdown | Availability
1 | Plant Fitter | BB0002 | Available |  |  | Maverick Double cab | 9 | 2 | 77.78%
2 | Plant Fitter | BB0006 | Available |  |  | Toyota Landcruiser Minespec | 33 | 1 | 96.97%
3 | Tyre Bay | LD0272 | Available |  |  | Toyota Landcruiser | 2 | 0 | 100%
4 | Ambulance | LD0283 | Available |  |  | Toyota Hilux | 2 | 0 | 100%
5 | Exploisive | LD0319 | Available |  |  | Maverick Man lift | 4 | 0 | 100%
6 | BEV | LD0375 | Available |  |  | Placer dumper | 1 | 0 | 100%
7 | Training Center | LD0401 | Available |  |  | Maverick king Cab c/w Crane | 3 | 0 | 100%
8 | Boilermaker | LD0405 | Not Available | Engine commision( No comminication between engine and Machine) | No solution from Fermel(Deutz EMR4 upgrade to EMR5) | Maverick Single cab Jam Pot | 1 | 0 | 100%
9 | Itireleng | LD0409 | Available |  |  | Bird Machine | 1 | 0 | 100%
10 | Hyd Fitter | LD0413 | Available |  |  | Bob Cat | 2 | 0 | 100%
11 | Instrumentation | LD0421 | Available |  |  | Maverick King Cab NO Crane | 2 | 0 | 100%
12 | Geology | LD0422 | Available |  |  | ROROs | 5 | 1 | 80%
13 | Electricians | LD0445 | Available |  |  | TOTAL | 65 | 4 | 93.85%
14 | Plant Fitter | LD0452 | Available
15 | Hyd Fitter | LD0512 | Available
16 | Main West | LD0520 | Not Available | Front axle making noise - (SOS - EOS)
17 | Hyd Fitter | LD0555 | Available
18 | Traimming | LD0556 | Available
19 | Drill Shop | LD0568 | Available
20 | Electricians | LD0569 | Available
21 | Mechanics | LD0570 | Available
22 | X Cut | LD0571 | Available
23 | Central | LD0572 | Available | Not accelerating - (09:27 - 14:05)
24 | Utility TMM | LD0573 | Not Available | Oil drain plug threats are stripped out - (SOS - EOS)
25 | Construction | LD0574 | Available
26 | Security | LD0595 | Available
27 | Rock Engneering | LD0604 | Available
28 | Construction | LD0606 | Available
29 | Mechanics | LD0607 | Available
30 | Traimming | LD0608 | Available
31 | Hyd Fitter | LD0609 | Available
32 | Plant Fitter | LD0610 | Available
33 | Main West | LD0611 | Maintenance | Service & found out that Center portion is worn out(making noise when driving) needs new center portion | center portion was replaced December 2025
34 | Hyd Fitter | LD0612 | Available
35 | Construction | LD0613 | Available
36 | Mechanics | LD0614 | Available
37 | Boilermaker | LD0615 | Available | Not accelerating - (07:24 - 09:21)
38 | Plant Fitter | LD0620 | Not Available | Strata (Surface decline & No acces to the gat, its locked ) - (SOS - EOS)
39 | Sim 2 | LD0622 | Available
40 | Training Center | LD0624 | Available
41 | Central | LD0625 | Available
42 | Electricians | LD0626 | Available | Not accelerating - (SOS - 10:54)
43 | SWD | LD0627 | Available
44 | Manager | LD0628 | Available
45 | Drill Shop | LD0635 | Available
46 | Boilermaker | UV0071 | Available
47 | Sampling | UV0074 | Available
48 | Sampling | UV0075 | Available
49 | Logistics | UV0078 | Not Available | Propshaft - (SOS - EOS) | Ordered 06 Oct 2025 (No stock at fermel)
50 | Logistics | UV0079 | Available
51 | Logistics | UV0081 | Available | Loose pawns - (12:45 - 13:12)
52 | Logistics | UV0082 | Available
53 | Logistics | UV0086 | Available
54 | Plant Fitter | UV0088 | Available
55 | Hyd Fitter | UV0091 | Not Available | Wiring - (SOS - 12:36) I - Tag not box not working - (12:36 - EOS)
56 | Utility TMM | UV0094 | Available
57 | Survey | UV0100 | Available
58 | Survey | UV0101 | Available
59 | Sanitec | UV0103 | Available
60 | Logistics | UV0116 | Available | Puncture - (10:15 - 12:04)
61 | Logistics | UV0045 | Available
62 | Mining | LD0646 | Available
63 | Electricians | LD0643 | Available
64 | Plant Fitter | LD0644 | Available
65 | BEV | LD0645 | Available
LABOUR
| Chargehand | 1/1
| Mech | 5/8 | X 1 annual leave
| Auto | 2/4 | x1 on sick leave untill April /x1 at training center as from last year
| Semi skilled | 2/2