## Slide 1
SHAFTS & WINDERS_HEAL
You Can Help By: Please provide an update on: Adjustments (Package) for Shaft & Winder Personnel to ensure Scares Skills are retained…. Please provide an update on: Assist with Winder Permit Rectifications + Winder Exemptions to DMPR…. Discuss and Motivate Memo for Shafts & Winders Services Supervisor Position with EM Assisting Michael who will be Taking over from Monday the 9th of Feb 2026 Thank You for Your Support!!!!
Highlights: Steady Water supply from Vaal Gamagarra Water Supply
Emerging Issues: Low compliment of Fitters and Riggers in Mechanical Section is still putting pressure on the Section Massive impact of providing full Maintenance of Changehouses of all 3 x Shafts…. Additional Low compliment due to: 1 x WTF: RFA Related issue
Lowlights: Positions to be filled taking considerable time to complete: 1 x WTFitter: @ Head-Hunting Stage: 2. Plumber Contractor currently not on site due to PP360 related issues 3. Power Outage Experienced during this week
Priorities: Shaft Repair Work with Solrock Team_will de-establish in Jan2026 Employee Engagement/Resignations Engagement with SGM: Busy with IDP’s sessions with Team Shaft Exam with Machinery Inspector Shaft Dewatering – Pump Test_Scheduled for Jan2026_Revised Date: Feb 2026 DMPR Instruction on Shafts & Winders Prep for Opportunity Maintenance during Power outage to repair Cap-Banks at Consumer Substation

## Slide 2
SHAFTS & WINDERS_HEAL
Highlights: Annual Shaft Schedule on Par (Next 2 x Slides)
JAN | 
 | EMT's/MRT's
 | DECEL TESTS
FEB | 
 | NCH2_PW_BE
 | NCH3_PW_BE
 | NCH2_SHAFT_GUIDE REPL
 | NCH2_3-7LVL_CHUTE LINERS
MARCH | 
 | NCH2_SHAFT_GUIDE REPL
 | NCH2_PW_FE
 | NCH3_PW_FE
 | NCH2_RW_FE
 | NCH2_PW_DYNAMICS
 | NCH3_PW_DYNAMICS
 | GL_PW_DYNAMICS
 | NCH2_RW_DYNAMICS
APRIL | 
 | EMT's/MRT's
 | DECEL TESTS
 | NCH2_REMOVE OLD CABLES
 | NCH2_3-7LVL_LDB LINERS
 | NCH2_PW_ANNUAL MHE
 | NCH3_PW_ANNUAL MHE
 | GL_PW_ANNUAL MHE
 | NCH2_RW_ANNUAL MHE
 | NCH2_PW_ANNUAL EHE
 | NCH3_PW_ANNUAL EHE
 | GL_PW_ANNUAL EHE
 | NCH2_RW_ANNUAL EHE

## Slide 3
SHAFTS & WINDERS_HEAL
Highlights: Annual Shaft Schedule on Par (Next Slide)
MAY | 
 | NCH2_SHAFT_GUIDE REPL
JUNE | 
 | NCH2_PW_STATICS
 | NCH3_PW_STATICS
 | GL_PW_STATICS
 | NCH2_RW_STATICS
 | NCH2_3-7LVL_LDB LINERS
JULY | 
 | NCH2_3-7LVL_LDB LINERS
 | DECEL TESTS
AUG | 
 | NCH2_3-7LVL_LDB LINERS

## Slide 4
SHAFTS & WINDERS_HEAL
Highlights: Annual Shaft Schedule on Par (Next Slide)_Depicting upcoming work for Nov2025 & Dec2025
SEP | 
 | NCH2_PW_DYNAMICS
 | NCH3_PW_DYNAMICS
 | GL_PW_DYNAMICS
 | NCH2_RW_DYNAMICS
OCT | 
 | NCH3_PW_FE
 | NCH2_PW_FE
 | GL_PW_FE
 | NCH2_RW_FE
 | NCH2_3-7LVL_LDB LINERS
 | NCH3_PW_MRT
 | NCH2_PW_MRT
 | GL_PW_MRT
 | NCH2_RW_MRT
NOV | 
 | NCH2_REPL_BUNTON 13
 | NCH2_3-7LVL_LDB LINERS
 | NCH3_PW_LVL 1 AUDIT
 | NCH2_PW_LVL 1 AUDIT
 | GL_PW_LVL 1 AUDIT
 | NCH2_RW_LVL 1 AUDIT
DEC | 
 | NCH3_PW_LVL 1 AUDIT
 | NCH2_PW_LVL 1 AUDIT
 | GL_PW_LVL 1 AUDIT
 | NCH2_RW_LVL 1 AUDIT
 | NCH2_SHAFT WORK_BUNTONS
 | NCH2_SILO TOP_REPLACE LINERS

## Slide 5
SHAFTS & WINDERS_HEAL
Highlights: Annual Shaft Schedule 2026
JAN | 
 | EMT's/MRT's
 | DECEL TESTS
FEB | 
 | NCH2_PW_BE
 | NCH3_PW_BE
 | NCH2_SHAFT_GUIDE REPL
 | NCH2_3-7LVL_CHUTE LINERS
MARCH | 
 | NCH2_SHAFT_GUIDE REPL
 | NCH2_PW_FE
 | NCH3_PW_FE
 | NCH2_RW_FE
 | NCH2_PW_DYNAMICS
 | NCH3_PW_DYNAMICS
 | GL_PW_DYNAMICS
 | NCH2_RW_DYNAMICS
APRIL | 
 | EMT's/MRT's
 | DECEL TESTS
 | NCH2_REMOVE OLD CABLES
 | NCH2_3-7LVL_LDB LINERS
 | NCH2_PW_ANNUAL MHE
 | NCH3_PW_ANNUAL MHE
 | GL_PW_ANNUAL MHE
 | NCH2_RW_ANNUAL MHE
 | NCH2_PW_ANNUAL EHE
 | NCH3_PW_ANNUAL EHE
 | GL_PW_ANNUAL EHE
 | NCH2_RW_ANNUAL EHE