## Eng Weekly report
Weekly Summary Report
Shaft | Nchwaning 2 | [6 empty] | Plan YTD | Actual YTD | Plan MTD | Actual MTD | Variance
[7 empty] | ROM | 1065195 | 953317 | 126888 | 117666 | -9222
Week - Date to | 2026-02-20 | 2026-02-27 |  |  |  |  | Plant | 978254 | 945313 | 113499 | 105197 | -8302
Safety
| YTD | No wk | Remarks
MTC | 1 | 0
LTI | 0 | 0
PD | 6 | 0
Incidents Reported | 1 | 0
Labour
| Plan | Actual | Leave | Not Specified | % AT Work |  | Remarks
Fri | 215 | 173 | 35 | 7 | 80.47%
Mon | 215 | 178 | 19 | 18 | 82.79%
Tue | 215 | 177 | 17 | 21 | 82.33%
Wed | 215 | 176 | 16 | 23 | 81.86%
Thur | 215 | 173 | 16 | 26 | 80.47%
Sat |  |  |  | 0 | #DIV/0!
Sun |  |  |  | 0 | #DIV/0!
Cost
Remarks
Planned Weekend/Public Holiday Work
Description |  |  |  |  | Done | Not Done | Remarks
Suport production and belt cleaning at 2West Plant
Extend BCU cable at South Block
DT0176 replace brake cooling pipes
HD67 and RT56 maintenance
FL0114 replace E20 box
UV0066 replace engine
| Fri | Mon | Tue | Wed | Thu | Average
DT | 77% | 86% | 73% | 87% | 94% | 83.4%
FL | 91% | 83% | 86% | 82% | 75% | 83.4%
HD | 93% | 96% | 97% | 83% | 92% | 92.2%
RT | 87% | 92% | 94% | 86% | 88% | 89.4%
SR | 99% | 79% | 86% | 95% | 95% | 90.8%
| 96% |  |  |  |  | 96%
TMM Status SOS (Friday Morning) : | [12 empty] | 5042
| Plan | Actual
HD | 6 | 6
RT | 6 | 6
DT | 10 | 10
FL | 6 | 6
SR | 6 | 6
Charge up UV`s | 3 | 2 | UV138 - low hydraulic pressure
RORO/Flat deck UV`s | 3 | 3
Weekly Primary TMM Maintenance Overview
Challenges
HD64 - Rig with long boom is tripping at 28N and also a new Mini-sub needs to be established at 28N.

## Compliance Report
Weekly Asset Care Compliance Report
Don’t change Formula's
| Week Ending | 2026-02-26
| Shaft / Area | NCHW II UG
| Fleet / Equipment | Planned | Actual | Schedule Compliance | Target | Unit late for service (y/n) | Unit book back on time after service(y/n) |  | Week-end Service | Reasons for Non-Compliance
| DT | 4 | 4 | 100% | 100%
| FL | 1 | 1 | 100% | 100%
| HD | 3 | 4 | 133.3% | 100%
| RT | 3 | 3 | 100% | 100%
| SR - Service Compliance | 0 |  |  | 100%
| Support Equipment | 11 | 7 | 63.64% | 100% |  |  |  |  | We experienced a labour shortage due to sick leave and breakdowns on 8seaters vehicles.so UV87 and 133 are scheduled for service on Friday, and LD0633, 647, and are planned for the weekend.
| SR - Weekly Inspection | 8 | 8 | 100% | 100%
Service Pre-Inspection
| Fleet / Equipment | Planned | Actual | Schedule Compliance | Target | Work order number | Remarks
| DT | 0 | 0 |  | 95%
| FL | 1 | 1 | 100% | 95%
| HD | 2 | 2 | 100% | 95%
| RT | 4 | 4 | 100% | 95%
| SR - Service Compliance | 3 | 3 | 100% | 95%
| Support Equipment | 6 | 6 | 100% | 95%
Condition monitoring / Oil samples
| Fleet / Equipment | Engine - Plan | Engine- Received | Transmission - Plan | Transmission - Receive | Axle - plan | Axle - Receive | % Compliance | Reasons for Non-Compliance |  |  | Paperwork Correct | Paperwork Incorrect | Urgent Oil Samples | Workorder Generated
| DT | 4 | 4 |  |  |  |  | 100% | [5 empty] | 0
| FL | 1 | 1 |  |  |  |  | 100% | [5 empty] | 0
| HD | 0 | [11 empty] | 0
| RT | 0 | [11 empty] | 0
| SR | 0 | 0 | [10 empty] | 0
| Support Equipment | 11 | 7 |  |  |  |  | 63.64% | We experienced a labour shortage due to sick leave and breakdowns on 8seaters vehicles.so UV87 and 133 are scheduled for service on Friday, and LD0633, 647, and are planned for the weekend. |  |  |  |  | 0
Remember Readings
Oil Filtration
FA0007 - HYDR DRILL W/S | Equipment nr | Oil Type | Start Reading | End Reading | Comments |  | ISO Standard
| HD0068 | AZOLLA | 22.21.16 | 20.19.13
| RT0032 | AZOLLA | 21.20.18 | 19.17.16
| RT0062 | AZOLLA | 20.18.15 | 18.17.12
| HD0053 | AZOLLA | 22.19.15 | 16.13.8
| RT0050 | AZOLLA | 21.19.12 | 19,16,9
FA0001 - TMM W/S
| DT0121 | Multigrade | 11/6/0 | 18/15/13
| DT0122 | Multigrade | 9/3/0 | 18/14/11
| DT0128 | Multigrade | 12/8/0 | 17/13/12
| FL0066 | Multigrade | 11/7/0 | 18/14/10
| Inspection done by: | Planned Over-Inspections | Total Number of Inspections Completed | Corrective Work | Wo Number | % Completed | Remarks for not comply
| UTILITY FOREMAN | 11 | 7 |  |  | 63.64% | We experienced a labour shortage due to sick leave and breakdowns on 8seaters vehicles.so UV87 and 133 are scheduled for service on Friday, and LD0633, 647, and are planned for the weekend.
| MECHANIC FOREMAN | 6 | 6 |  |  | 100%
| DRILLS FOREMAN | 5 | 5 |  |  | 100%
| Engineer | 1 | 1 |  |  | 100%
| Electrical Foreman | 4 | 4 |  |  | 100%
Plant Foreman
| GES Plant | 3 | 3 |  |  | 100%
| GES TMM | 1 | 1 |  |  | 100%
| Equipment ID | Date of Inspection | Inspection Performed by | Findings and Defects Completed |  |  | Additional Follow-up Work |  |  | WO No. | Status
| HD0068 | 21/02/2026 | WILL | NONE |  |  | IN ORDER |  |  | 1926094
| HD0035 | 22/06/2026 | WILL | NONE |  |  | IN ORDER |  |  | 1926729
| RT0040 | 22/02/2026 | WILL | NONE |  |  | IN ORDER |  |  | 1924637
| RT0062 | 22/02/2026 | WILL | NONE |  |  | IN ORDER |  |  | 1924232
| RT0032 | 23/02/2026 | WILL |  | NONE |  |  |  | IN ORDER | 1925522
| HD0053 | 25/02/2026 | WILL | NONE |  |  | IN ORDER |  |  | 1924271
| RT0050 | 26/02/2026 | WILL | NONE |  |  | IN ORDER |  |  | 1926668
| HD0063 | 26/02/2026 | WILL | NONE |  |  | IN ORDER |  |  | 1931318
| DT0159 | 20/02/2026 | Mosala | None |  |  | I.O |  |  | 1932958
| DT0121 | 23/02/2026 | Mosala | None |  |  | I.O |  |  | 1912679
| DT0122 | 24/02/2026 | Mosala | None |  |  | I.O |  |  | 1900843
| DT0128 | 24/02/2026 | Mosala | None |  |  | I.O |  |  | 1849305
| FL0066 | 26/02/2026 | Mosala | None |  |  | I.O |  |  | 1930874
| UV0138 | 26/02/2026 | Mosala | None |  |  | I.O |  |  | 1930879
| LD0450 | 20/02/2026 | Dlamini | None |  |  | I.O
| UV0084 | 24/02/2026 | Dlamini | None |  |  | I.O |  |  | 1853834
| LD0519 | 22/02/2026 | Dlamini | Diesel bracket broken off |  |  | I.O |  |  | 1 802 247
| LD0557 | 26/02/2026 | Dlamini | Transmission and gearbox topped and aux battery was low replaced |  |  | I.O |  |  | 1932963
| LD0630 | 24/02/2026 | Dlamini | None |  |  | I.O |  |  | 1919200
| LD0576 | 19/02/2026 | Dlamini | None |  |  | I.O |  |  | 1941049
| UV0054 | 23/02/2026 | Dlamini | None
| RT0032 | 23/02/2026 | Clinton | NONE |  |  | I.O |  |  | 1925523
| RT0040 | 24/02/2026 | Clinton | Replace Q2 main circuit breaker |  |  | I.O |  |  | 1926671
| HD0053 | 25/02/2025 | Clinton | NONE |  |  | I.O |  |  | 1926728
| RT0050 | 26/02/2026 | Clinton | NONE |  |  | I.O |  |  | 1926669

## Water Consumption
Water Consumption Management
Dates: 13 Feb. -20 Feb. | Shaft |  | Fire Dams
Water Type | Down | Out | In | Out
Process | 0 | 4991
Portable | 164 | 0
Fire |  |  |  |  | Fire figures are not available yet

## Quality Report
Weekly Asset Care Compliance Report Nchwaning II UG
| Week Ending | 2026-02-26 | [6 empty] | NB: PLEASE DO NOT EDIT ON YELLOW COLUMN
| Shaft / Area | Nch II U/G
Weekly Quality Service Report
|  |  | Mining |  |  |  | 77.08% | Engineering | [5 empty] | 89.58%
| Schedule Date | TMM Unit Number | Actual Time Available In Workshop - < 7:00 AM | 07:00 AM - 50% 08:00 AM - 25% 09:00 AM - 0% | Machine Clean for Maintenance | No - 0% Yes - 50% |  | Pre inspection & Operator Engagement - 3 Days Before Service Done | No - 0% Yes - 25% | Actual Service Duration - Plan 6 Hours | 6Hrs - 50% 5Hrs - 40% 4Hrs - 30% 3Hrs - 20% 2Hrs - 10% 1Hrs - 0% | Machine Tested and Over Inspected by Supervisor | No - 0% Yes - 25% |  | Time of first breakdown | Completed Service Workorder number | Actual Hrs on service date
1 | 2026-02-20 | DT0159 | 8:00 | 25% | Yes | 50% | 75% | Yes | 25% | 6HRS | 50% | Yes | 25% | 100% |  | 1932958 | 7711
2 | 2026-02-20 | HD0035 | 8:00 | 25% | Yes | 50% | 75% | Yes | 25% | 6HRS | 50% | Yes |  | 75% | 0.43 |  | 2786
3 | 2026-02-20 | RT0040 | 8:00 | 25% | Yes | 50% | 75% | Yes | 25% | 6HRS | 50% | Yes | 25% | 100%
4 | 2026-02-20 | UV0054 | 7:00 | 50% | Yes | 50% | 100% | Yes | 25% | 6HRS | 50% | Yes | 25% | 100%
5 | 2026-02-20 | LD0450 | 7:00 | 50% | Yes | 50% | 100% | Yes | 25% | 6HRS | 50% | Yes | 25% | 100%
6 | 2026-02-21 | LD0647 |  |  |  |  | 0% | [6 empty] | 0%
7 | 2026-02-23 | DT0121 | 8:00 | 25% | Yes | 50% | 75% | Yes | 25% | 6HRS | 50% | Yes | 25% | 100% |  | 1912679 | 8969
8 | 2026-02-23 | HD0068 | 8:00 | 25% | Yes | 50% | 75% | No | 25% | 6HRS | 50% | Yes | 25% | 100% | 0 |  | 506
9 | 2026-02-23 | UV0084 | 7:00 | 50% | Yes | 50% | 100% | Yes | 25% | 6HRS | 50% | Yes | 25% | 100%
10 | 2029-02-23 | LD0519 | 7:00 | 50% | Yes | 50% | 100% | Yes | 25% | 6HRS | 50% | Yes | 25% | 100%
11 | 2026-02-24 | DT0128 | 8:00 | 25% | Yes | 50% | 75% | Yes | 25% | 6HRS | 50% | Yes | 25% | 100% |  | 1849305 | 15442
12 | 2026-02-24 | RT0062 | 8:00 | 25% | Yes | 50% | 75% | Yes | 25% | 6HRS | 50% | Yes | 25% | 100% | 2.3 |  | 213
13 | 2026-02-24 | UV0133 |  |  |  |  | 0% | [6 empty] | 0%
14 | 2026-02-24 | LD0557 | 10:00 | 0% | Yes | 50% | 50% | Yes | 25% | 6HRS | 50% | Yes | 25% | 100%
15 | 2026-02-25 | DT0122 | 8:00 | 25% | Yes | 50% | 75% | Yes | 25% | 6HRS | 50% | Yes | 25% | 100% |  | 1900843 | 17264
16 | 2026-02-25 | HD0053 | 8:00 | 25% | Yes | 50% | 75% | Yes | 25% | 6HRS | 50% | Yes | 25% | 100% | 0 |  | 3745
17 | 2026-02-25 | UV0138 | 8:00 | 25% | Yes | 50% | 0% | Yes | 25% | 6HRS | 50% | Yes | 25% | 100% |  | 1930879 | 717
18 | 2026-02-26 | FL0066 | 8:00 | 25% | Yes | 50% | 75% | Yes | 25% | 6HRS | 50% | Yes | 25% | 100% |  | 1930874 | 13066
19 | 2026-02-26 | RT0050 | 9:00 | 0% | Yes | 50% | 50% | Yes | 25% | 5HRS | 40% | Yes | 25% | 90% | 1.2 |  | 1901
20 | 2026-02-26 | UV0087 |  |  |  |  | 0% | [6 empty] | 0%
21 | 2026-02-26 | LD0633 |  |  |  |  | 0% | [6 empty] | 0%
22 | 2026-02-25 | LD0630 | 7:15 | 50% | Yes | 50% | 100% | Yes | 25% | 6HRS | 50% | Yes | 25% | 100%
23 | 2026-02-20 | LD0576 | 7:00 | 50% | Yes | 50% | 100% | Yes | 25% | 6HRS | 50% | Yes | 25% | 100%
24 | [6 empty] | 0% | [6 empty] | 0%
25 | [6 empty] | 0% | [6 empty] | 0%
26 | [6 empty] | 0% | [6 empty] | 0%
27 | [6 empty] | 0% | [6 empty] | 0%
28 | [6 empty] | 0% | [6 empty] | 0%
29 | [6 empty] | 0% | [6 empty] | 0%
30 | [6 empty] | 0% | [6 empty] | 0%
31 | [6 empty] | 0% | [6 empty] | 0%
32 | [6 empty] | 0% | [6 empty] | 0%
33 | [6 empty] | 0% | [6 empty] | 0%
Note on N9: Botshelo Gae: operators are not available during the pre inspection

## Fermel Weekly
N 2
No | Area / Owner | TMM Type | TMM No. | Breakdown | Comment | OEM Assistance Required |  | Utility Machine | Total | Breakdown | Availabile
| RORO UV'S FERMEL | [6 empty] | Maverick Dble Cab STD Load Bin | 11 | 3 | 72.73%
2 | BRP/Logistics | Liberator Roll On Roll Off | UV0054 |  | Available |  |  | Maverick Man Lift | 4 | 1 | 75%
3 | BRP/Logistics | Liberator Roll On Roll Off | UV0059 |  | Available |  |  | Liberator Roll On Roll Off | 6 | 0 | 100%
4 | Roadways | Liberator Roll On Roll Off | UV0061 |  | Available |  |  | Placer dumper | 1 | 0 | 100%
5 | BRP/Logistics | Liberator Roll On Roll Off | UV0118 |  | Available |  |  | Maverick king Cab c/w Crane | 3 | 0 | 100%
6 | BRP/Logistics | Fermel Placer Dumper | UV0119 |  | Available |  |  | Maverick Single cab Jam Pot | 1 | 0 | 100%
7 | BRP/Logistics | Liberator Roll On Roll Off | UV0120 |  | Available |  |  | Maverick 12 Man Trooper | 3 | 1 | 66.67%
8 | BRP/Logistics | Liberator Roll On Roll Off | UV0133 |  | Available |  |  | Scaler | 8 | 0 | 100%
| MAVERICK UV'S | [6 empty] | Toyota landcuiser ambulance | 1 | 0 | 100%
10 | Williams /drill mec | Maverick King Cab NO Crane | UV0069 |  | Available |  |  | Maverick king Cab with no Crane | 2 | 0 | 100%
11 | Kal Tire | Maverick King Cab NO Crane | UV0072 |  | Not Avaiable |  |  | Toyota landcruiser | 34 | 3 | 91.18%
12 | Williams | Maverick king Cab c/w Crane | UV0087 |  | Available |  |  |  | 74 | 8 | 89.19%
13 | Fitters | Maverick king Cab c/w Crane | UV0090 |  | Available
14 | Gae | Maverick king Cab c/w Crane | UV0092 |  | Available
15 | Sanitation | Maverick Single cab Jam Pot | UV0102 |  | Available
MAVERICK LDO'S
17 |  |  | LD0378
18 | Roadways | Maverick Dble Cab STD Load Bin | LD0407 |  | Available
19 | Williams /drill mec | Maverick Dble Cab STD Load Bin | LD0408 |  | Available
20 | Mining/28 section | Maverick Dble Cab STD Load Bin | LD0411 |  | Available
21 | Technicians | Maverick Dble Cab STD Load Bin | LD0414 |  | Available |  | Labour for the week including Nightshift
22 | Themba fire fighters | Maverick Dble Cab STD Load Bin | LD0415 |  | Available |  | Foreman | 1 of 0
23 | Boilermakers | Maverick Dble Cab STD Load Bin | LD0419 |  | Available |  | Chargehand | 1 of 0 |  | x1 relieving
24 | Technicians | Maverick Dble Cab STD Load Bin | LD0426 | We have bought the engine directly from Fermel based on the fact it was an EMR4 engine. During commissioning by Deutz, it has been realized that this supplied engine is EMR 5 engine which is was even comminicated betwwen us BRMO and deutz | Not Available |  | Mechanics | 9 of 5 |  | x1 AD, x1 AL, x1 night ,x1 relieving
25 | Explosive | Maverick Dble Cab STD Load Bin | LD0450 |  | Available |  | Auto Electrician | 3 of 2 |  | X1 AD
26 | Capital graben | Maverick Dble Cab STD Load Bin | LD0508 | The machine is currently standing due to a faulty side shaft. We are wait parts. | Not Available |  | Semi skilled | 3 of 2 |  | x1 Annual leave ,x1 night
27 | Gae | Maverick Dble Cab STD Load Bin | LD0509 | The leaf spring broke off. It has been removed and we are currently busy repairing | Not Available |  | Leaners | 1 of 1
28 | Capital graben | Maverick Dble Cab STD Load Bin | LD0519 |  | Available
29
30
32
33
34
35
36
37
| MAVERICK LDO'S TROPPER | [5 empty] | DELAY:
39 | Fitters | Maverick 12 Man Trooper | LD0477 | Just reported now with engine cut off ,we're not show if it is hydraulic ,coolant | Not Available
40 | Mining/28 section | Maverick 12 Man Trooper | LD0523 |  | Available
41 | Construction | Maverick 12 Man Trooper | LD0532 |  | Available
42 | MAVERICK UV'S MANLIFTS | [5 empty] | PRIORITY FOR THE NEXT SHIFT
43 | Geologist | Maverick Man Lift | UV0077 | GES has stopped the order and any further work. The Fermel OEM was not able to fix the man lift, and the invoice was nearly R500,000, which we cannot approve since work was done . GES has therefore placed the invoice on hold. As per discussion, we will pay half of the amount. and the plan was to send the machine to Johannesburg for further repairs, remove the bucket, and convert the UV to a flatdeck | Not Available
44 | Survey | Maverick Man Lift | UV0098 |  | Available
45 | Survey | Maverick Man Lift | UV0099 |  | Available
46 | Geologist | Maverick Man Lift | UV0123 |  | Available |  | SERVICE UPDATES
TOYOTA CRUISER LDO'S
47 | Ambulance | Toyota Cruiser 4x4 emergency vehicle | LD0 341 |  | Available
48 | Capital graben | Toyota Cruiser 4x4/Trimming-Connie | LD0 553 |  | Available
49 | Lebolo/2west2body | Toyota Cruiser 4x4/mining -Lebelo | LD0 554 |  | Available
50 | Connie Trimming | Toyota Cruiser 4x4/Trimming-Connie | LD0 557 | machine in for service | Not Available
51 | Fitters w/shop | Toyota Cruiser 4x4/fitter plant-Lebogang | LD0 575 | During the over inspection after driver reported the noisy, we observed that the machine was making noise while in motion. A stop-and-fix was conducted, and work is currently in progress on the CV joint and the backlash on the centre portion was found to be out of spec ,parts arranged few arrived , | Not Available
52 | Electrical w/shop | Toyota Cruiser 4x4 /electrician-Hansie | LD0 576 |  | Available
53 | Connie Mining | Toyota Cruiser 4x4/mining-Connie | LD0 577 |  | Available
54 | Peace | Toyota Cruiser 4x4/mining -portgter | LD0 578 | During offloading of vehicle, we noticed a leak on the CV and a noise when turning to the right side. After disassembly, it was found that the centre portion , the CV joint was worn out. New parts were arranged ,dis-assy and assembled. Today the diff was then loaded onto LD0621 and sent to the surface. Installation will be carried out, and an update will be provided in the daily report | Not Available
55 | Christo | Toyota Cruiser 4x4/mining-christo | LD0 579 |  | Available
56 | Training Center | Toyota Cruiser 4x4/training center | LD0 580 |  | Available
57 | Potgieter | Toyota Cruiser 4x4/Mining 28 section | LD0 581 |  | Available
5
55
56
AARD UV'S
58 | Duba Utility | aard-uv60-diesel tank | UV0053 | Machine went for L9 Upgrade. | Not Available
59 | Hansie Louw | aard-uv60 | UV0084 |  | Available
| Roadways | aard-uv80-water tank truck | UV0121 | still standing with engine oil filter and control has no option for waiting part | Not Available
61 | Capital-Graben | aard-uv80 | UV0130 |  | Available
62 | Construction | aard-uv60 | UV0139 |  | Available
63 | Construction | aard-uv60 | UV0140 |  | Available
66 | Construction | aard-uv60
67
68
SCALER'S
72 | Scaler | Scaler | SR0029 |  | Available
73 | Scaler | Scaler | SR0033 |  | Available
74 | Scaler | scaler graben Capital Tel 5013 | SR0036 |  | Available
75 | Scaler | scaler 17upper 74 Portigter | SR0042 |  | Available
76 | Scaler | scaler 17upper 74 Portigter | SR0045 |  | Available
77 | Scaler | scaler graben Capital Tel 5013 | SR0046 |  | Available
| Scaler | Scaler Mining | SR0053 |  | Available
78 | Scaler | Scaler Mining | SR0054 |  | Available
TOYOTA CRUISER WITH HIAB'S
78 | Life Tmm | Toyota Cruiser 4x4 | LD0 589* |  | Available
79 | Duba Utility | Toyota Cruiser 4x4 | LD0 590* |  | Available
80 | Didi-Boilermaker | Toyota Cruiser 4x | LD0 592* |  | Available
81 | Izak Bothman KalTire | Toyota Cruiser 4x4/Kal Tire | LD0 593* |  | Available
82 | Fitters Lebogang | Toyota Cruiser 4x4/ | LD0 594 |  | Available
83 | Duba Utility | Toyota Cruiser 4x4/ | LD0 621 |  | Available
84 | Life Tmm | Toyota Cruiser 4x4/ | LD0 633 |  | Available
TOYOTA CRUISER TROPPER'S
84 | Karl Roadways | Toyota Cruiser 4x4/ | LD0 596 |  | Available
85 | Geologist&Survey | Toyota Cruiser 4x4/ | LD0 605 |  | Available
86 | Mining-Peace | Toyota Cruiser 4x4/ | LD0 629 |  | Available
| Mining | Toyota Cruiser 4x4/ | LD0 649 |  | Available
| Duba Utility | Toyota Cruiser 4x4/ | LD0 650 |  | Available
TOYOTA CRUISER WITHOUT HIAB'S
87 | William Tel:5429 | Toyota Cruiser 4x4/ lube | LD0 591 |  | Available
88 | Duba Utility | Toyota Cruiser 4x4- single cap | LD0 621* |  | Available
89 | Electrician tel:5416 | Toyota Cruiser 4x4/ | LD0 623 |  | Available
90 | Electrician tel:5416 | Toyota Cruiser 4x4/ | LD0630* |  | Available
91 | William Tel:5429 | Toyota Cruiser 4x4/ | LD0631 |  | Available
92 | Boilers | Toyota Cruiser 4x4 | LD0634* |  | Available
93 | Izak Botham | Toyota Cruiser 4x4/ drill rod carrier | LD0636* |  | Available
| Manyafunyafu | CRUISER SINGLE CAP Hiab | LD0642 |  | Available
| William Tel:5429 | CRUISER SINGLE CAP Hiab | LD0647 |  | Available
| Life Tmm | CRUISER SINGLE CAP Hiab | LD0648 |  | Available
| Strata team | CRUISER SINGLE CAP Hiab | LD0658 |  | Available
| Project | CRUISER 8 Seater | LD0675 |  | Available

## Block Chute
0 | Details | FEEDER BELT CHUTE |  |  | TIPS 1&2 | [5 empty] | Area xyz
| Supervisor/artisan who assisted with unblocking | M.Diergaardt | TK Mosiane | J Benson | M.Diergaardt | TK Mosiane | J Benson | M.Diergaardt | TK Mosiane | J Benson
02/02/2026 | Reason for blockage | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages
| Time of blockage | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Supervisor/artisan who assisted with unblocking | Xaba | GKP SETSHEDI | J Benson | Xaba | GKP SETSHEDI | J Benson | Xaba | GKP SETSHEDI | J Benson
03/02/2026 | Reason for blockage | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages
| Time of blockage | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Supervisor/artisan who assisted with unblocking | Xaba | GKP SETSHEDI | J Benson | Xaba | GKP SETSHEDI | J Benson | Xaba | GKP SETSHEDI | J Benson
04/02/2026 | Reason for blockage | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages
| Time of blockage | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Supervisor/artisan who assisted with unblocking | Xaba |  |  | Xaba |  |  | Xaba
05/02/2026 | Reason for blockage | No Blockages |  |  | No Blockages |  |  | No Blockages
| Time of blockage | N/A |  |  | N/A |  |  | N/A
| Supervisor/artisan who assisted with unblocking | Xaba | GKP SETSHEDI |  | Xaba | GKP SETSHEDI |  | Xaba | GKP SETSHEDI
06/02/2026 | Reason for blockage | No Blockages | No Blockages |  | No Blockages | No Blockages |  | No Blockages | No Blockages
| Time of blockage | N/A | N/A |  | N/A | N/A |  | N/A | N/A
| Supervisor/artisan who assisted with unblocking | L OOR | GKP SETSHEDI | Xaba | L OOR | GKP SETSHEDI | Xaba | L OOR | GKP SETSHEDI | Xaba
09/02/2026 | Reason for blockage | wedged and pile up |  |  | No Blockages |  | No Blockages | No Blockages |  | No Blockages
|  | of flat big rocks | No Blockages | No Blockages | N/A | No Blockages |  | N/A | No Blockages
| Time of blockage | 10h30-10h54&11h45-12h00 | N/A | N/A |  | N/A | N/A |  | N/A | N/A
| Supervisor/artisan who assisted with unblocking | J Benson | TK Mosiane | Xaba | J Benson | TK Mosiane | Xaba | J Benson | TK Mosiane | Xaba
10/02/2026 | Reason for blockage | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages
| Time of blockage | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Supervisor/artisan who assisted with unblocking | J Benson | TK Mosiane | Xaba | J Benson | TK Mosiane | Xaba | J Benson | TK Mosiane | Xaba
11/02/2026 | Reason for blockage | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages
| Time of blockage | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Supervisor/artisan who assisted with unblocking | J Benson | TK Mosiane | Xaba | J Benson | TK Mosiane | Xaba | J Benson | TK Mosiane | Xaba
12/02/2026 | Reason for blockage | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages
| Time of blockage | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
13/02/2026 | Supervisor/artisan who assisted with unblocking | J Benson | TK Mosiane | Xaba | J Benson | TK Mosiane | Xaba | J Benson | TK Mosiane | Xaba
| Reason for blockage | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages
| Time of blockage | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
15/02/2026 | Supervisor/artisan who assisted with unblocking | J Benson |  |  | J Benson |  |  | J Benson
| Reason for blockage | No Blockages |  |  | No Blockages |  |  | No Blockages
| Time of blockage | N/A |  |  | N/A |  |  | N/A
16/02/2026 | Supervisor/artisan who assisted with unblocking | M.Diergaardt | TK Mosiane | J Benson | M.Diergaardt | TK Mosiane | J Benson | M.Diergaardt | TK Mosiane | J Benson
| Reason for blockage | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages
| Time of blockage | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
17/02/2026 | Supervisor/artisan who assisted with unblocking | Xaba | TK Mosiane | J Benson | Xaba | TK Mosiane | J Benson | Xaba | TK Mosiane | J Benson
| Reason for blockage | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages
| Time of blockage | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
18/02/2026 | Supervisor/artisan who assisted with unblocking | Xaba | TK Mosiane | J Benson | Xaba | TK Mosiane | J Benson | Xaba | TK Mosiane | J Benson
| Reason for blockage | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages
| Time of blockage | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
19/02/2026 | Supervisor/artisan who assisted with unblocking | Xaba | TK Mosiane |  | Xaba | TK Mosiane |  | Xaba | TK Mosiane
| Reason for blockage | No Blockages | No Blockages |  | No Blockages | No Blockages |  | No Blockages | No Blockages
| Time of blockage | N/A | N/A |  | N/A | N/A |  | N/A | N/A
20/02/2026 | Supervisor/artisan who assisted with unblocking | Xaba | TK Mosiane | J Benson | Xaba | TK Mosiane | J Benson | Xaba | TK Mosiane | J Benson
| Reason for blockage | No Blockages | No Blockages | No Blockages | No Blockages | Big rocks in the throat | Big rocks in the throat, blast feeder | No Blockages | Big rocks in the throat | Big rocks in the throat, blast feeder
| Time of blockage | N/A | N/A | N/A | N/A | 18h35-EOS | 20h45-21h21 | N/A | 18h00-EOS | 20h45-21h21
21/02/2026 | Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
22/02/2026 | Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
23/02/2026 | Supervisor/artisan who assisted with unblocking | J Benson | TK Mosiane | Xaba | J Benson | TK Mosiane | Xaba | J Benson | TK Mosiane | Xaba
| Reason for blockage | No Blockages | No Blockages | Big Rocks wedged in the chute | No Blockages | No Blockages | No blockage | No Blockages | No Blockages | No blockage
| Time of blockage | N/A | N/A | 00h10-00h31 | N/A | N/A | N/A | N/A | N/A | N/A
24/02/2026 | Supervisor/artisan who assisted with unblocking | J Benson | TK Mosiane | M.DIERGAARDT | J Benson | TK Mosiane | M.DIERGAARDT | J Benson | TK Mosiane | M.DIERGAARDT
| Reason for blockage | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages
| Time of blockage | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A
25/02/2026 | Supervisor/artisan who assisted with unblocking | J Benson | J Benson |  | J Benson | J Benson |  | J Benson | J Benson
| Reason for blockage | No Blockages | Big rocks pile up in chute |  | No Blockages | No Blockages |  | No Blockages | No Blockages
| Time of blockage | N/A | 16h40-17h00 |  | N/A | N/A |  | N/A | N/A
26/02/2026 | Supervisor/artisan who assisted with unblocking | J Benson | TK Mosiane | M.DIERGAARDT | J Benson | TK Mosiane | M.DIERGAARDT | J Benson | TK Mosiane | M.DIERGAARDT
| Reason for blockage | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages | No Blockages
| Time of blockage | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage